[NTD: FOR INSURANCE REASONS, THESE SUPPLEMENTARY CONDITIONS ARE NOT TO BE USED FOR PROJECTS WITH ROOF ASSEMBLIES INVOLVING ANY FORM OF “HOT ROOFING”.]

SUPPLEMENTARY CONDITIONS TO

STIPULATED PRICE CONTRACT

(CCDC 2 - 2020)

These Supplementary Conditions are made as of the ___ day of ____________, 20___ between UNIVERSITY OF VICTORIA (the “Owner”) and [CONTRACTOR] (the “Contractor”).  Other than the Supplementary Conditions contained herein, the Stipulated Price Contract (CCDC 2 - 2020) between the Owner and the Contractor remains in full force and effect (the “Contract”).  The Owner and the Contractor hereby agree to supplement and amend the Articles, Definitions and General Conditions of the Contract as set out herein. Notwithstanding General Condition 1.1.5, where there is anything in the Contract which is inconsistent with these Supplementary Conditions, the provisions of these Supplementary Conditions shall govern.  Throughout the Contract Documents, reference to the Articles, Definitions and General Conditions or a paragraph of the General Conditions shall include these Supplementary Conditions unless the context requires otherwise.  Where an Article, Definition General Condition or paragraph of the General Conditions is deleted by these Supplementary Conditions, the number of the remaining General conditions or paragraphs shall remain unchanged, unless stated otherwise herein, and the number of the deleted item will be retained but be unused.

| SC # | GC # | Supplementary Conditions |
| --- | --- | --- |
| ARTICLES |  |  |
|  | Article A-1 | Insert the following new paragraphs following paragraph 1.3: |
|  | “1.4 | At least seven (7) days prior to the commencement of the Work, the Contractor shall deliver to the Owner the following: .1 proof of all necessary permits, licenses, certificates and other authorizations required by all municipal, provincial or federal authorities, for the Work and proof of payment of all applicable fees; .2 certificates of insurance for all insurance policies required by this Contract; .3 the performance and labour and material payment bonds required by the Contract; .4 a construction schedule satisfactory to the Owner as required by paragraph 3.4, including in graphic form the proposed dates; .5 a schedule of values of the various parts of the Work as required by paragraph 5.2.4; and .6 proof that the Contractor has obtained WorkSafe BC or Workers Compensation Board registration and clearance. |
|  | 1.5 | The Contractor shall give the Owner a minimum of forty-five (45) days’ written notice that the Contractor will meet (or not meet) the date set in out in Article A-1 paragraph 1.3 for Ready-for-Takeover.” |
|  | Article A-4 | In paragraph 4.1 of Article A-4 – CONTRACT PRICE, the Owner and the Contractor acknowledge and agree that notwithstanding the phrase “which excludes Value Added Taxes” that appears in the first line, British Columbia Provincial Sales Tax (if applicable) is included in the Contract Price. In paragraph 4.2 of Article A-4 – CONTRACT PRICE, the Owner and the Contractor acknowledge and agree that the amount shown for Value Added Taxes consists only of Goods and Services Tax (GST) and does not include British Columbia Provincial Sales Tax (which is included in the Contract Price). |
|  | Article A-5 | In paragraph 5.1.3 of ARTICLE A-5 – PAYMENT, delete the phrase “the issuance of the” in the first line and substitute the phrase “receipt of the Consultant’s”. |
|  | Article A-8 | In paragraph 8.1 of Article A-8 – SUCCESSION, immediately before the word “assigns” in the second line, insert the word “permitted”. |
| DEFINITIONS |  |  |
|  | Definitions: | Insert the following new definitions: |
|  |  | Applicable Law Applicable Law means all public laws, statutes, ordinances, codes, acts, orders, by-laws, rules, regulations, Governmental Consents, binding policies and guidelines, and requirements of all Governmental Authorities, which now or hereafter, may be applicable to and enforceable against the Owner, the Contractor or the Work, or any part thereof, including those relating to employment, zoning, building, safety, environment and health. |
|  |  | As-Built Drawings As-Built Drawings shall have the meaning given in paragraph 3.9.2 – DOCUMENTS AT THE SITE. |
|  |  | Deficiency Retention Deficiency Retention shall have the meaning given in paragraph 5.4.11 – SUBSTANTIAL PERFORMANCE OF THE WORK AND PAYMENT OF HOLDBACK. |
|  |  | Environmental Law Environmental Law means all Applicable Law relating to the environment, health, occupational health and safety, product liability or transportation of dangerous goods, including but not limited to any laws relating to the storage, generation, use, handling, manufacture, processing, labeling, advertising, sale, display, transportation, treatment, reuse, recycling, or release of Hazardous Substances. |
|  |  | Force Majeure Force Majeure means any of the following events or circumstances (or combination of events and circumstances): (i) any strikes, lockouts, or labour disputes affecting the construction industry generally in the Place of the Work (and not only the Contractor, its Subcontractors or Suppliers) provided that such strike, lockout or labour dispute is not initiated by the Contractor, its Subcontractors or Suppliers or their respective employees; or (ii) enemy or hostile actions, sabotage, war, blockades, insurrections, riots, epidemics, pandemics, nuclear and radiation activity or fall-out, civil disturbances, explosions, fire and acts of God (provided that adverse weather conditions shall not be considered acts of God, even if such conditions are unusually adverse), in each case which: (a) are beyond the control of the party affected by that event or circumstance or both; (b) cause delay in, or prevent performance by, the affected party of any of its obligations under this Contract; and (c) cannot be prevented, overcome or remedied by the exercise by the affected party of a reasonable standard of care and diligence. |
|  |  | Governmental Authority Governmental Authority means any federal, provincial, territorial, regional, municipal or local government authority, quasi-governmental authority, court, government or self-regulatory organization, commission, board, tribunal, organization, or any regulatory, administrative or other agency or any political or other subdivision, department, or branch of any foregoing having legal jurisdiction in any way over the Owner, any aspect of the performance of the Contract, in each case to the extent it has or performs legislative, judicial, regulatory, administrative or other functions within its jurisdiction. |
|  |  | Governmental Consent Governmental Consent means any license, right, permit, franchise, privilege, registration, direction, decree, consent, order, permission, approval, or authority to be issued or provided by, a Governmental Authority. |
|  |  | Hazardous Substance Hazardous Substance means any hazardous product or waste, contaminant, pollutant, toxic substance, deleterious substance, dangerous good or reportable substance that is identified or described in or defined by any Environmental Law and any other substance the storage, generation, use, handling, manufacture, processing, labeling, advertising, sale, display, transportation, treatment, reuse, recycling, or release of which is prohibited, controlled, regulated or licensed by any Governmental Authority. |
|  |  | Indirect Loss Indirect Loss means any: (i) loss of revenue, loss of profits, loss of use, loss of contract, loss of goodwill, loss of business or loss of business opportunity; (ii) exemplary or punitive damages; or (iii) indirect or consequential loss of any nature (except to the extent included in a third party claim), claimed or suffered by a party. |
|  |  | Owner Confidential Information Owner Confidential Information means all information relating to the Work and any process, technology or system relating thereto, the design, construction, operation, maintenance or any other aspect of the Place of the Work, or relating to the nature of the Owner’s business and affairs, including this Contract, which the Contractor directly or indirectly receives or acquires from the Owner or the Owner’s representative or anyone on behalf of the Owner or the Owner’s representative either in writing or verbally, or through observation of the Place of the Work or the Work. |
|  |  | Person Person includes any individual, company, corporation, partnership, firm, trust, sole proprietorship, government or government agency, authority or entity howsoever designated or constituted. |
|  |  | Qualified Environmental Professional Qualified Environmental Professional means an independent expert registered and in good standing with an appropriate professional organisation constituted under Applicable Law, licenced and qualified to provide advice and assistance in relation to the storage, use, handling, transportation, removal, treatment, remediation or disposal of Hazardous Substances. |
|  |  | Recovery Schedule Recovery Schedule refers to documentation and information produced, prepared and provided by the Contractor to the Consultant and Owner to establish to the satisfaction of the Consultant and Owner how the progress of the Work or any aspect of the Work will be expedited to ensure that the construction schedule, and specific milestone dates from time to time designated by the Owner acting reasonably, will be met. The Recovery Schedule will provide full and sufficient detail to enable the Consultant and Owner to be satisfied as to the precise steps that the Contractor will take to expedite progress, including but not limited to detailing any proposed increase in manpower, any proposed overtime work, any proposed re-sequencing of Work and any proposed expediting of deliveries of Product or Construction Equipment. |
|  | Definitions: | Delete the definitions of “Change Directive”, “Change Order”, “Consultant”, “Contractor”, “Owner”, “Subcontractor” and “Supplier” replace with the following: Change Directive A Change Directive is a written instruction prepared by the Consultant or the Owner and signed by the Owner directing the Contractor to proceed with a change in the Work prior to the Owner and the Contractor agreeing upon adjustments (if any) in the Contract Price and/or the Contract Time. Change Order A Change Order is a written amendment to this Contract prepared by the Consultant or the Owner and signed by the Owner and the Contractor stating their agreement upon: - a change in the Work; - the method of adjustment or the amount of the adjustment in the Contract Price, if any; and - the extent of the adjustment in the Contract Time, if any. Consultant The Consultant is the person or entity engaged by the Owner and identified as such in the Agreement. The Consultant is the Architect, the Engineer or entity licensed to practise in the province or territory of the Place of the Work. The term Consultant means the Consultant or the Consultant’s authorized representative. Contractor The Contractor is the person or entity identified as such in the Agreement. The term Contractor means the Contractor or the Contractor's authorized representative as designated to the Owner in writing. Owner The Owner is the person or entity identified as such in the Agreement. The term Owner means the Owner or the Owner’s authorized agent or representative as designated to the Contractor in writing, but does not include the Consultant. For the purposes of this Contract, the terms “Owner”, “University of Victoria”, “UVic” and “University” shall be considered synonymous. Subcontractor Subcontractor means any "subcontractor" as defined under the Builders Lien Act (British Columbia), in respect of any part or parts of the Work. Supplier Supplier means any "material supplier" as defined under the Builders Lien Act (British Columbia), in respect of any Products forming part of the Work. |
| GENERAL CONDITIONS |  |  |
|  | GC 1.1.2 | Delete paragraph 1.1.2 in its entirety and substitute the following: |
|  | “1.1.2 | The Contract Documents are complementary, and what is required by one shall be as binding as if required by all. The Contract, including the Contract Documents, constitutes the entire agreement between the Owner and the Contractor with respect to the Work.” |
|  |  | Delete paragraphs 1.1.3 and 1.1.4 in their entirety and substitute the following: |
|  | “1.1.3 | The Contractor shall review the Contract Documents and shall report promptly to the Consultant and the Owner any error, inconsistency or omission the Contractor may discover. The Contractor shall promptly request clarifications upon discovery of errors, inconsistencies or omissions in the Contract Documents. Additional work made necessary because of a failure by the Contractor to request clarification promptly following the discovery of such errors, inconsistencies or omissions by the Contractor in the Contract Documents shall be carried out and completed at the Contractor’s sole expense. Provided that the Contractor has exercised the degree of care and skill required pursuant to GC 3.14 – CONTRACTOR STANDARD OF CARE, the Contractor shall not be responsible for damage resulting from such errors, inconsistencies or omissions in the Contract Documents which the Contractor did not reasonably discover. If the Contractor does discover any error, inconsistency or omission in the Contract Documents, the Contractor shall promptly report the matter to the Owner and Consultant, and the Contractor shall not proceed with the portion of the Work affected until the Contractor has received corrected or missing information from the Owner or Consultant, as required. |
|  | 1.1.4 | Intentionally blank.” |
|  | GC 1.1.5 | Insert the following paragraph at the end of paragraph 1.1.5: |
|  |  | “.6 architectural Drawings shall have precedence over structural, plumbing, mechanical, electrical and landscape Drawings insofar as outlining, determining and interpreting conflicts over the required design intent of all architectural layouts and architectural elements of construction, it being understood that the integrity and installation of systems designed by the Consultant are to remain with each of the applicable drawing disciplines. Subject to the foregoing, if any Drawings or Specifications conflict with any other Drawings or Specifications, then the more stringent requirements shall govern.” |
|  | GC 1.1.9 | Insert the following at the end of paragraph 1.1.9: “The Specifications are divided into divisions and sections for convenience but shall be read as a whole and neither such divisions nor anything else contained in the Contract Documents will be construed to place responsibility on the Consultant to settle disputes among the Subcontractors and Suppliers in respect of such divisions. The Drawings are, in part, diagrammatic and intended to convey the scope of the Work and indicate general and appropriate location, arrangement and sizes of fixtures, equipment and outlets. The Contractor shall obtain more accurate information about the locations, arrangements and sizes from study and coordination of the Drawings, including Shop Drawings, and shall become familiar with conditions and spaces affecting these matters before proceeding with the Work. Where site conditions require reasonable minor changes in indicated locations and arrangements, the Contractor shall make such changes at no additional cost to the Owner. Similarly, where known conditions or existing conditions interfere with new installation and require relocation, the Contractor shall include such relocation in the Work, unless otherwise indicated on the Drawings or Specifications. The Contractor shall arrange and install fixtures and equipment in such a way as to conserve as much headroom and space as possible.” |
|  | GC 1.1.10 | Delete paragraph 1.1.10 in its entirety and substitute the following: |
|  | “1.1.10 | Specifications, Drawings, models, and copies thereof furnished by the Consultant are and shall remain the Consultant’s property, with the exception of the signed Contract sets, which shall belong to each party to this Contract provided that the Owner shall be permitted to use all of the Drawings, Specifications, copies thereof and models for the purpose of completing the Work in the event of termination of the Contract or for the purposes of future additions or alterations to the Project. All Specifications, Drawings, and models furnished by the Consultant are to be used only with respect to the Work and are not to be used on other work. These Specifications, Drawings and models are not to be copied or altered in any manner without the written authorization of the Consultant.” |
|  | GC 1.1.11 | Insert the following new paragraphs following paragraph 1.1.11: |
|  | “1.1.12 | The Specifications and Drawings are integral and any work necessary and described in (or reasonably inferred from) the Specifications but not shown on the Drawings, or necessary and shown on (or reasonably inferred from) the Drawings but not described in the Specifications, shall be deemed to be part of the Work and carried out as part of the Contract. |
|  | 1.1.13 | Notwithstanding paragraph 1.1.5, where the Contract Documents contain inconsistent provisions dealing with the same matter, or if there is any inconsistency in the Drawings or any conflict between the Drawings and the Specifications, the Contractor shall provide the better quality or greater quantity of Work or materials, as applicable, unless the Owner or Consultant otherwise directs in writing. |
|  | 1.1.14 | Wherever the words “approved”, “satisfactory”, “selected”, “directed”, “permitted”, “inspected”, “instructed”, “required”, “submit”, “ordered” are used in the Contract Documents, it shall be understood that the words “by the Owner” follow, unless the context provides otherwise.” |
|  | GC 1.4.1 | Delete paragraph 1.4.1 in its entirety and substitute the following: |
|  | “1.4.1 | The Owner may assign the Contract or a portion thereof without the consent of the Contractor. The Contractor will not assign the Contract or any portion thereof without the prior written consent of the Owner (which consent shall be in the Owner’s absolute discretion and may be arbitrarily withheld).” |
|  | GC 1.4.1 | Insert the following new paragraph following paragraph 1.4.1: |
|  | “1.4.2 | The Contractor hereby consents to the assignment of the Contract by the Owner as security for any financing arranged by the Owner relating to the Project, and the Contractor agrees to execute any consent document reasonably requested by the Owner or its lenders in relation thereto.” |
|  | GC 1.5 | Insert the following new General Condition following GC 1.4: |
|  | “GC 1.5 | CONFIDENTIALITY AND ADVERTISING |
|  | 1.5.1 | The Contractor shall keep confidential all Owner Confidential Information and shall not, without the prior written consent of the Owner, use such Owner Confidential Information other than for the purposes of performing the Work, or disclose such Owner Confidential Information, except to its professional advisors, to the Consultant or to Subcontractors or Suppliers who need to know such matters for purposes of the Work and are bound by confidentiality restrictions no less stringent than those in this GC 1.5 - CONFIDENTIALITY AND ADVERTISING. |
|  | 1.5.2 | The matters that are subject to the confidentiality requirements of this GC 1.5 - CONFIDENTIALITY AND ADVERTISING shall not include information that: (i) has become generally available to the public other than as a result of a disclosure by the Contractor, Subcontractors or Suppliers or any of their respective representatives in breach of paragraph 1.5.1, (ii) was available to the other party or its representatives on a non-confidential basis before the date of the Contract, or (iii) becomes available to a party or any of their respective representatives on a non-confidential basis from a Person other than the first-mentioned party or any of its representatives who is not, to the knowledge of such other party or its representatives, otherwise bound by confidentiality obligations to such first-mentioned party in respect of such information or otherwise prohibited from transmitting the information to such first-mentioned party or its representatives. |
|  | 1.5.3 | The Contractor shall obtain the Owner’s prior written approval of any public advertising, promotion, press release or any other general publicity matter in which the name or trademarks of the Owner or any details of the Project are used, or in which words are used from which any connection with the Owner’s name or trademarks may be inferred. The Contractor shall not allow or permit any public ceremony in connection with the Work, without the prior, written permission of the Owner. The Contractor shall not erect or permit the erection of any signage or advertising at the Place of the Work without the prior written approval of the Owner.” |
|  | GC 2.2.6 | Delete paragraph 2.2.6 in its entirety, and substitute the following |
|  | “2.2.6 | Where required pursuant to an agreement between the Owner and the Consultant, the Consultant will be, in the first instance, the interpreter of the requirements of the Work.” |
|  | GC 2.2.12 | Insert the following at the end of paragraph 2.2.12: “If in the opinion of the Contractor, the Supplemental Instructions require an adjustment in the Contract Price or in the Contract Time, the Contractor shall within ten (10) Working Days of receipt of a Supplemental Instruction provide the Consultant with a written notice to that effect. In the event that the Contractor needs additional information to determine whether a Supplemental Instruction requires an adjustment in the Contract Price or in the Contract Time, it may issue a written request to the Consultant seeking such additional information. Following receipt of such information, the Contractor shall, within ten (10) Working Days of receipt of such additional information provide the Consultant with the written notice prescribed in the first sentence of this paragraph 2.2.12. Failure to provide written notification within the time stipulated in this paragraph 2.2.12 shall be deemed an acceptance of the Supplemental Instruction by the Contractor without adjustment in the Contract Price or the Contract Time.” |
|  | GC 2.2.18 | Insert the following new paragraphs after paragraph 2.2.18: |
|  | “2.2.19 | In any written or printed notice to the Contractor in respect of any general, special or other repairs, or of any work of any nature required to be done under any of the provisions of the Contract, or of any other matter, it shall not be obligatory upon the Consultant or the Owner to specify minutely or in detail everything required, nor to specify by measurement the exact extent thereof, or the precise spot or spots where the work or material may be defective or faulty or where any of the requirements of the Specifications have not been observed; but a reference in such notice to the clause or clauses bearing upon the matter, and a description of the locality in general terms, and sufficiently clear, in the opinion of the Consultant or the Owner, to indicate where the defect or trouble exists and such notice shall be deemed to be sufficient notice. |
|  | 2.2.20 | The Consultant shall be the “payment certifier” for the purposes of the Builders Lien Act (British Columbia) in respect of amounts due to the Contractor under the Contract, including all lien holdback funds. The Contractor acting alone shall be the “payment certifier” for the purposes of the Builders Lien Act (British Columbia) in respect of amounts due to any “subcontractor” as defined under the Builders Lien Act (British Columbia). Certification by the Contractor in respect of amounts due to any “subcontractor” as defined under the Builders Lien Act (British Columbia) or in respect of completion of a subcontract, and release of holdback monies by the Owner in respect of amounts due to any such “subcontractor” in connection with such certification by the Contractor, shall not be taken as acceptance or approval by the Owner of any of the Work of such “subcontractor”. |
|  | 2.2.21 | The Consultant’s services will be performed solely for the benefit of the Owner and no Contractor, Subcontractor, Supplier or other third party shall have any claim against the Consultant as a result of the performance or non-performance of the Consultant’s services. The Contractor shall include this provision in any contracts it makes with its Subcontractors, Suppliers and others and shall require such Subcontractors, Suppliers and others to include the same term in their contract with sub-subcontractors, sub-suppliers and others.” |
|  | GC 2.3.2-2.3.3 | Delete paragraphs 2.3.2 and 2.3.3 in their entirety and substitute the following: |
|  | “2.3.2 | If Work is designated for review, tests, inspections or approvals in the Contract Documents, or by the Consultant’s or the Owner’s instructions, or by the laws or ordinances of the Place of the Work, the Contractor shall give the Consultant and the Owner reasonable notification within no less than 24 hours of when the Work will be ready for review and inspection. The Contractor shall arrange for and shall give the Consultant and the Owner reasonable notification within no less than 24 hours of the date and time of inspections by other authorities. |
|  | 2.3.3 | The Contractor shall furnish promptly to the Consultant and the Owner two copies of certificates and inspection reports relating to the Work.” |
|  | GC 2.3.4 | In the first and second line of paragraph 2.3.4, delete “special” and substitute “review,”. In the third line of paragraph 2.3.4, insert “review,” before “inspections”. |
|  | GC 2.3.5 | Delete paragraph 2.3.5 in its entirety and substitute the following: |
|  | “2.3.5 | The Consultant or the Owner may order any portion or portions of the Work to be examined to confirm that such work is in accordance with the requirements of the Contract Documents. If the Work is not in accordance with the requirements of the Contract Documents, the Contractor shall correct the Work and pay the cost of examination and correction at the Contractor’s expense. If the Work is in accordance with the requirements of the Contract Documents, the Owner shall pay the cost of examination and restoration.” |
|  | GC 2.3.7 | Insert the following new paragraphs after paragraph 2.3.7: |
|  | “2.3.8 | In addition to the specific tests and inspections contemplated in the Contract Documents, general review during construction by the Owner or Consultant may be undertaken so that the Owner can be informed as to the quality of the Contractor’s performance. The review does not relieve the Contractor of the responsibility to carry out its own quality control and to make the Work conform to the Contract requirements. The Contractor is solely responsible for the quality of the Work and shall undertake any quality control activities specified in the Contract Documents or, if none is specified, as may be reasonably required to ensure such quality. The Contractor shall provide copies of applicable quality control checklists within ten (10) Working Days of the award of this Contract. |
|  | 2.3.9 | If, in the reasonable opinion of the Owner or Consultant, the rate of progress or quality of the Work is unsatisfactory or unnecessary interruptions occur in the continuous performance of the Work, the cost for additional inspections by the Owner or Consultant shall be deducted by the Owner from the Contract Price. The Owner’s or Consultant’s decision as to the extent and cost of additional inspection necessary because of unsatisfactory or tardy performance of the Contract shall be final. |
|  | 2.3.10 | If the Consultant is required to make more than one review of rejected work or if the Consultant performs additional reviews due to failure of the Work to comply with the application for status of completion made by the Contractor, the Contractor will compensate the Owner for such additional Consultant services including expenses incurred. Adjustment for such compensation will be made as outlined under Part 6 of the General Conditions – CHANGES IN THE WORK.” |
|  | GC 2.4.1 | Insert “or the Owner” in the first sentence after the words “by the Consultant”. Insert the following at the end of paragraph 2.4.1: “The Contractor shall prioritize and expedite the correction of any defective work which in the sole determination of the Owner, adversely affects the day to day operation of the Owner.” |
|  | GC 2.4.3 | Insert “or the Owner” in the first sentence after the words “opinion of the Consultant”. |
|  | GC 3.1.2 | Insert the following new paragraphs after paragraph 3.1.2: |
|  | “3.1.3 | Prior to commencing any individual procurement, fabrication and construction activities, the Contractor shall verify, at the Place of the Work, all relevant measurements and levels necessary for the proper and complete fabrication, assembly and installation of the Work and shall further carefully compare such field measurements and conditions with the requirements of the Contract Documents. Where dimensions are not included or contradictions exist, or exact locations are not apparent, the Contractor shall immediately notify the Consultant and the Owner in writing and obtain written instructions from the Owner before proceeding with any part of the affected Work. |
|  | 3.1.4 | Subject to the other provisions of GC 3.1 – CONTROL OF THE WORK, the Contractor agrees that, it shall fully comply with any policies or procedures of the Owner which are relevant to any activities of the Contractor to be performed under the Contract. The Contractor further agrees that it will use reasonable efforts to inquire from the Owner if such policies or procedures exist for any activity of the Contractor to be performed under the Contract. The Owner agrees that it will use reasonable efforts to communicate to the Contractor policies or procedures it may have relevant to such activities. The Owner will provide copies of policies relevant to the Contractor’s activities upon request. The policies include: .1 Discrimination and Harassment Policy .2 Sexualized Violence Prevention and Response Policy .3 Parking Policy .4 Occupational Health & Safety Policy .5 At Risk Behaviour Policy .6 University Smoking Policy .7 Traffic and Parking Regulations .8 Sustainability Policy .9 University Signage Policy .10 Building and Grounds Usage Policy .11 Furnishings, Fittings, Finishes and Artwork Policy.” |
|  | GC 3.2.2 | Delete paragraph 3.2.2.1 in its entirety and insert “Intentionally blank”. |
|  | GC 3.2.3 | Delete the word “and” from the end of paragraph 3.2.3.3. Insert the following at the end of paragraph 3.2.3.4: “Failure by the Contractor to so report shall invalidate any claims against the Owner by reason of the defects or deficiencies in the work of Other Contractors or Owner’s own forces except those deficiencies not then reasonably discoverable; and” |
|  | GC 3.2.3 | Insert the following new paragraph following paragraph 3.2.3.4: |
|  |  | “.5 subject to GC 9.4 – CONSTRUCTION SAFETY and where paragraph 3.2.3.2 of GC 3.2 – CONSTRUCTION BY THE OWNER OR OTHER CONTRACTORS applies, assume overall responsibility for compliance with all aspects of the applicable health and safety legislation in the Place of the Work for the Owner’s own forces and for Other Contractors performing work identified in the Contract Documents, including all of the responsibilities of the “prime contractor” as that terms is defined in the Workers Compensation Act (British Columbia).” |
|  | GC 3.2.6 | Delete paragraph 3.2.6 in its entirety and insert “Intentionally blank”. |
|  | GC 3.2.6 | Insert the following new paragraphs after paragraph 3.2.6: |
|  | “3.2.7 | Entry by the Owner’s own forces or by Other Contractors does not constitute acceptance of the Work and does not relieve the Contractor of its responsibilities to complete the Contract. |
|  | 3.2.8 | The placing, installation and connection of work by the Owner’s own forces or by Other Contractors on and to the Work does not relieve the Contractor of its responsibility under any warranties set out in the Contract.” |
|  | GC 3.3.2 | Replace the word “law” with the words “Applicable Law” in paragraph 3.3.2. |
|  | GC 3.4.1 | Delete paragraph 3.4.1 in its entirety and replace with the following: |
|  | “3.4.1 | The Contractor shall: .1 within seven (7) calendar days prior to site mobilization, prepare and submit to the Owner and the Consultant for their review and acceptance, a construction schedule that indicates the timing of the activities of the Work and provides sufficient detail of the critical events and their inter-relationship to demonstrate the Work will be performed in conformity with the Contract Time and in accordance with the Contract Documents. The construction schedule shall comply with the requirements specified in the Specifications in relation to the construction schedule. The Contractor shall provide the construction schedule and any successor or revised schedules to the Owner in electronic format and paper copy. Once accepted by the Owner and the Consultant, the construction schedule submitted by the Contractor shall become the baseline construction schedule, and the Contractor shall not amend the accepted construction schedule without the prior written consent of the Owner; .2 at all times perform the Work required hereunder as diligently and expeditiously as is consistent with the highest professional standards and the orderly progress of the Work, within the Contract Time and in accordance with the construction schedule and any revisions thereto, in order to maintain the desired development and construction schedule for the Project, and in order not to delay the Work or any aspect of the construction of the Project; .3 monitor and report on the progress of the Work on a weekly basis relative to the baseline construction schedule, or any successor or revised schedule accepted by the Owner pursuant to GC 3.4 – CONSTRUCTION SCHEDULE, update the schedule on a monthly basis and provide Notice in Writing to the Consultant and the Owner of any variation from the baseline or slippage in the schedule; .4 at all times provide sufficient personnel to accomplish its services within the Contract Time and in accordance with the construction schedule and any revisions thereto; .5 provide the expertise and resources, such resources including sufficient manpower and equipment, as are necessary to maintain progress under the accepted baseline construction schedule or revised schedule accepted by the Owner pursuant to GC 3.4 – CONSTRUCTION SCHEDULE; .6 provide overtime work without change to the Contract Price if such work is deemed necessary by the Contractor to meet the construction schedule; and .7 ensure that the Contract Price includes all costs required to phase or stage the Work.” |
|  | GC 3.4.1 | Insert the following new paragraphs following paragraph 3.4.1: |
|  | “3.4.2 | The Contractor is responsible for performing the Work within the Contract Time. Any schedule submissions revised from the accepted baseline construction schedule or revised schedule accepted by the Owner during construction are not deemed to be approved extensions to the Contract Time. All extensions to the Contract Time must be made in accordance with the Contract Documents. |
|  | 3.4.3 | If, at any time, it should appear to the Owner or the Consultant that the actual progress of the Work is behind schedule or is likely to become behind schedule, or if the Contractor has given notice of such to the Owner or the Consultant pursuant to subparagraph 3.4.1.3, the Contractor shall take appropriate steps to cause the actual progress of the Work to conform to the schedule or minimize the resulting delay and shall produce and present to the Owner and the Consultant a Recovery Schedule demonstrating how the Contractor will achieve the recovery of the construction schedule. If the Contractor intends to apply for a change in the Contract Price in relation to a Recovery Schedule, then the Contractor shall proceed in accordance with General Condition 6.5 – DELAYS. |
|  | 3.4.4 | The construction schedule must show and correspond to the breakdown of work shown on the schedule of values required by paragraph 5.2.4 and on the monthly progress claims so as to facilitate evaluation of applications for payment. |
|  | 3.4.5 | The Owner assumes the construction schedule to have monetary value. |
|  | 3.4.6 | Time shall in all respects be of the essence of this Contract. |
|  | 3.4.7 | The Contractor acknowledges and agrees that the Contractor may be required to proceed with the Work simultaneously with Other Contractors at the Place of the Work and agrees that it will not be entitled to nor will claim any additional compensation by reason of the fact that the Contractor is required to coordinate its work and share the facilities and construction area with Other Contractors.” |
|  | GC 3.5.1 | Delete the second sentence in its entirety and substitute the following: “The representative initially appointed by the Contractor must be satisfactory to the Owner. The Contractor’s appointed representative shall not be changed except for a valid reason. The Contractor’s appointed representative shall not be changed without consultation with and written acceptance by the Owner (such acceptance not to be unreasonably withheld).” |
|  | GC 3.5.2 | Delete paragraph 3.5.2 in its entirety and substitute the following: |
|  | “3.5.2 | Instructions given to the Contractor’s appointed representative shall be deemed to have been given to the Contractor, and the Contractor’s appointed representative shall have full authority to act on behalf of the Contractor and to bind the Contractor in matters related to this Contract.” |
|  | GC 3.5.2 | Insert the following new paragraph after paragraph 3.5.2: |
|  | “3.5.3 | The Owner may, for reasonable cause request that Contractor remove from the Project any supervisor, representative or employee of the Contractor or Subcontractors, or Suppliers, and the Contractor shall forthwith designate replacements who are acceptable to the Owner.” |
|  | GC 3.6.1 | Delete paragraph 3.6.1 in its entirety and substitute the following: |
|  | “3.6.1 | The Contractor shall preserve and protect the rights of the parties under the Contract with respect to work to be performed under subcontract, and shall: .1 enter into written contracts or written agreements with Subcontractors and Suppliers to require them to perform their work as provided in the Contract Documents; .2 incorporate the applicable terms and conditions of the Contract Documents into all written contracts or agreements with Subcontractors and Suppliers; .3 be as fully responsible to the Owner for acts and omissions of Subcontractors, Suppliers and any persons directly or indirectly employed by them as for acts and omissions of persons directly employed by the Contractor; and .4 for greater certainty, and further to paragraph 3.6.1.1 hereof, the Contractor (i) shall maintain a listing of all written contracts or written agreements with Subcontractors and Suppliers and (ii) shall, on the request of the Owner provide all particulars in respect of Subcontractors and Suppliers, including, if requested, a copy of any or all fully executed written contracts or written agreements with the Subcontractors and Suppliers.” |
|  | GC 3.6.2 | Insert the following at the end of paragraph 3.6.2: “The Contractor agrees not to change Subcontractors or Suppliers without the prior written consent of the Owner.” |
|  | GC 3.7.1 | In paragraph 3.7.1, insert the words “and its agents, Subcontractors and Suppliers and their employees” after the word “employees”. |
|  | GC 3.7.3 | Delete paragraph 3.7.3 in its entirety and substitute the following: |
|  | “3.7.3 | Unless otherwise specified in the Contract Documents, Products provided shall be new and shall conform to all current applicable specifications of the Canadian Standards Association, Canadian Standards Board or General Standards Board, ASTM, National Building Code, BC Building Code, National Fire Prevention Association and all governmental and regulatory authorities having jurisdiction at the Place of the Work. Products which are not specified shall be of a quality consistent with those specified, and their use acceptable to the Consultant and the Owner. Products brought on to the Place of the Work by the Contractor shall be deemed to be the property of the Owner, but the Owner shall be under no liability for loss thereof or damage thereto arising from any cause whatsoever. Such Products shall be at the sole risk of the Contractor.” |
|  | GC 3.7.3 | Insert the following new paragraphs after paragraph 3.7.3: |
|  | “3.7.4 | The Contractor represents and warrants that the Products provided in accordance with the Contract are not subject to any conditional sales contract or any security rights obtained by any third party which may subject any of the Products to seizure and/or removal from the Place of the Work. |
|  | 3.7.5 | The Contractor shall be responsible for the safe on-site storage of Products and their protection (including Products supplied by the Owner and Other Contractors to be installed under the Contract) in such ways as to avoid dangerous conditions or contamination to the Products or other Persons or property and in locations at the Place of the Work to the satisfaction of the Owner and the Consultant. |
|  | 3.7.6 | The Contractor shall provide and pay for all labour, materials, tools, construction machinery and equipment, transportation and any other facilities necessary to carry out the Work in accordance with the Contract Documents. |
|  | 3.7.7 | The Contractor will, at the request of the Owner or Consultant, remove from the Place of the Work any Person employed on the Work who, in the opinion of the Consultant or the Owner, is incompetent or has been conducting himself improperly and the Contractor shall not permit a Person so removed to remain on the Place of the Work or return to the Place of the Work.” |
|  | GC 3.8.2 | Insert the following at the end of paragraph 3.8.2: “The Contractor shall submit all Shop Drawings in triplicate and in reproducible form.” |
|  | GC 3.8.3 | Delete the word “applicable” before “field measurements” in paragraph 3.8.3.1. |
|  | GC 3.8.7 | Insert the following new paragraphs after paragraph 3.8.7: |
|  | “3.8.8 | The Contractor shall prepare a Shop Drawing schedule acceptable to the Owner and Consultant prior to the first application for payment. The Contractor shall submit a draft of the proposed Shop Drawing schedule to the Consultant and the Owner for approval. The draft Shop Drawing schedule shall clearly indicate the phasing of the Shop Drawing submissions. On approval of the Shop Drawing schedule, the Consultant and the Contractor shall jointly prepare a schedule of dates for the review and return of the Shop Drawings. The Consultant will review and return Shop Drawings and submittals in accordance with the schedule agreed to in this paragraph 3.8.8, or, in absence of such schedule, with reasonable promptness. If, for any reason, the Consultant cannot process the Shop Drawings and/or submittals within the agreed-upon schedule or with reasonable promptness, the Consultant shall notify the Contractor and they shall meet to review and arrive at an acceptable revised schedule. |
|  | 3.8.9 | The Contractor shall provide Shop Drawings in the form specified, or if not specified, as directed by the Consultant. |
|  | 3.8.10 | Shop Drawings which require approval of any legally constituted authority having jurisdiction shall be provided to such authority by the Contractor for approval. |
|  | 3.8.11 | The Contractor shall provide revised Shop Drawings to correct those which the Consultant rejects as inconsistent with the Contract Documents, unless otherwise directed by the Consultant. The Contractor shall notify the Consultant in writing of any revisions to the Shop Drawings other than those requested by the Consultant. |
|  | 3.8.12 | Reviewed Shop Drawings shall not authorize a change in the Contract Price and/or the Contract Time.” |
|  | GC 3.9 | Insert a new General Condition 3.9, General Condition 3.10, General Condition 3.11, General Condition 3.12, General Condition 3.13, General Condition 3.14 and General Condition 3.15: |
|  | “GC 3.9 | DOCUMENTS AT THE SITE |
|  | 3.9.1 | The Contractor shall keep one copy of the current Contract Documents, Supplemental Instructions, contemplated Change Orders, Change Orders, Change Directives, cash allowance disbursement authorizations, reviewed Shop Drawings, submittals, reports and records of meetings at the Place of the Work, in good order and available to the Owner and Consultant and their respective representatives. The Contractor shall keep a daily record of the Work for review by the Consultant and the Owner, and the record shall include the number of workers, the delivery of Products and the amount and location of Products incorporated in the Work, the daily weather and temperature range, incidents, damage, intrusions, losses, and other pertinent details relevant to the daily progress of the Work. |
|  | 3.9.2 | The Contractor shall maintain a set of Drawings on which the Contractor shall make any changes to the Work at the end of each week (such drawings, the “As-Built Drawings”). As-Built Drawings shall be kept in good order and shall be available to the Consultant, the Owner and their representatives for review at the Place of the Work. The Contractor shall record on the As-Built Drawings the changes in the Work as such changes occur. Changes in the Work shall be indicated on the As-Built Drawings by the use of coloured lines and suitable notations.” |
|  | GC 3.10 | USE OF THE WORK |
|  | 3.10.1 | The Contractor shall confine Construction Equipment, Temporary Work, storage of Products, waste products and debris, and operations of employees and Subcontractors to limits indicated by laws, ordinances, permits, or the Contract Documents and shall not unreasonably encumber the Place of the Work. |
|  | 3.10.2 | The Contractor shall not load or permit to be loaded any part of the Work with a weight or force that will endanger the safety of the Work. |
|  | 3.10.3 | The Owner and its representatives and Other Contractors shall have the right to enter and occupy the Project, in whole or in part, before the completion of the Work if, in the opinion of the Consultant, acting reasonably and following consultation with the Contractor, such entry or occupancy will not prevent or unreasonably interfere with the Contractor in the completion of the Work. If the Owner enters or occupies part of the Project then the Owner shall occupy that part of the Project in a manner which does not interfere with the Contractor’s performance of the remaining Work. |
|  | 3.10.4 | If work or storage areas in addition to areas provided by the premises are required, the Contractor shall be responsible for making arrangements to obtain the additional areas, whether adjacent to the premises or not, and for making permit and rental payments that may be required. |
|  | 3.10.5 | In carrying out the Work, the Contractor must minimize damage or injury to any adjacent property and, except as otherwise provided in this Contract, if injury or damage is done, it must make good the same, at its own expense, in the manner directed by, and to the satisfaction of, the Consultant and the Owner. The Contractor shall be responsible for any and all damages, or claims for damages for injury or accidents done or caused by it or its employees or agents, or resulting from the prosecution of the Work, or any of its operations, or caused by reason of the existence or location or condition of the Work, or of any materials, plant or machinery used thereon or therein, or which may happen by reason thereof, or arising from any act of commission or omission on its part, or on the part of any of its agents or employees, in connection with the Contract, and covenants and agrees to hold the Owner harmless and indemnified from all such damages and claims for damage, and in case of Contractor’s failure, neglect or omission to observe and perform faithfully and strictly, all the provisions of the Contract, the Owner may, either with or without notice (except where in this Contract, notice is specifically provided for, and then upon giving the notice therein provided for), take such steps, procure such material, plant, trucks and personnel, and do such work or things as it may deem advisable toward carrying out and enforcing the same, and any and all expenses so incurred may be deducted or collected by the Owner, and any such action by the Owner as it is herein empowered to take, shall not in any way relieve the Contractor or its surety from any liability under the Contract. |
|  | 3.10.6 | If the Contractor enters into the lands or buildings of the Province or of any municipality or of any person or enters into any highway or road under the jurisdiction and control of any public authority for the purpose of making any survey, examination, investigation, inspection or other arrangement or lays any pipes or appurtenances in, upon, through, over or under any highway or road under the jurisdiction and control of any public authority and in so doing disturbs any such lands, buildings, highways or roads, such lands, buildings, highways or roads shall be restored to their original condition without unnecessary delay. |
|  | 3.10.7 | The Contractor must (if it is practicable in the opinion of the Consultant) keep the roadway open for travel for the use of the public, for such width as the Consultant may direct. Where, in the opinion of the Consultant, it is not practicable to keep a roadway open for the full flow of traffic, it may permit the Contractor to close or partially close such roadway and to provide for a detour of the traffic or a part thereof. In each such case and before putting into effect the closure or detour, the Contractor shall present its proposal for closure or detour to any Governmental Authority having jurisdiction over any of the roadways which will be affected by the proposed closure of the said authority or authorities. The Contractor must provide a sufficient number of “NO THOROUGHFARE”, “DETOUR” or other proper notices, which it must cause to be placed and maintained in good order in conspicuous places wherever any roadway, sidewalk, or thoroughfare is torn up or dangerous, and so long as it remains unsafe or unfinished. When any Work is carried on at night, the Contractor must supply, at its own expense, a sufficient number of electric or other approved and efficient lights, to enable the same to be done in an efficient and satisfactory manner, and the Consultant shall have the power to order additional lights to be put on at the Contractor’s expense if in the opinion of the Consultant, they are, or may be, required. |
|  | 3.10.8 | The method of use and the character of all explosives shall be subject to the approval of the Consultant. The Contractor shall ensure that the charges of explosives used by the Contractor and the time at which they are exploded shall be such as not to cause damage to person or property or to cause unreasonable inconvenience. Explosives shall be properly housed and protected as provided by Applicable Law, and no explosives known to have deteriorated shall be used. Approved methods of handling and thawing of frozen explosives shall be followed, and the greatest care shall be exercised at all times by the Contractor in blasting operations. |
|  | GC 3.11 | CUTTING AND REMEDIAL WORK |
|  | 3.11.1 | The Contractor shall perform the cutting and remedial work required to make the affected parts of the Work come together properly. |
|  | 3.11.2 | The Contractor shall co-ordinate the Work to ensure that the cutting and remedial work is kept to a minimum. |
|  | 3.11.3 | Should the Owner, the Consultant, Other Contractors, or anyone employed by them directly or indirectly be responsible for ill-timed work necessitating cutting or remedial work to be performed, the cost of such cutting or remedial work shall be valued as provided in GC 6.1 – OWNER'S RIGHT TO MAKE CHANGES, GC 6.2 – CHANGE ORDER and GC 6.3 – CHANGE DIRECTIVE. |
|  | 3.11.4 | Cutting and remedial work shall be performed by specialists familiar with the Products affected and shall be performed in a manner to neither damage nor endanger the Work. |
|  | GC 3.12 | CLEANUP |
|  | 3.12.1 | The Contractor shall maintain the Work in a safe and tidy condition and free from the accumulation of waste products, debris, snow and ice, other than that caused by the Owner, other contractors or their employees. |
|  | 3.12.2 | Before applying for Substantial Performance of the Work as provided in GC 5.4 – SUBSTANTIAL PERFORMANCE OF THE WORK AND PAYMENT OF HOLDBACK, the Contractor shall remove waste products and debris, other than that resulting from the work of the Owner, Other Contractors or their employees, and shall leave the Place of the Work clean and suitable for use or occupancy by the Owner. The Contractor shall remove products, tools, Construction Equipment, and Temporary Work not required for the performance of the remaining work. |
|  | 3.12.2 | Prior to application for the final payment, the Contractor shall remove any remaining products, tools, Construction Equipment, Temporary Work, and waste products and debris, other than those resulting from the work of the Owner, Other Contractors or their employees. |
|  | 3.12.3 | In the event that the Contractor fails to comply with its obligations in this General Condition 3.12, then the Owner or the Consultant may give the Contractor twenty-four (24) hours’ written notice to meet its obligations. Should the Contractor fail to meet its obligations pursuant to this General Condition 3.12 within the twenty-hour (24) hour period immediately following the delivery of such notice, the Owner may remove such waste, debris, snow and/or ice and deduct from payments otherwise due to the Contractor, the Owner’s costs for such cleanup, including a reasonable mark-up for administration. |
|  | GC 3.13 | OCCUPANCY NEAR THE WORK |
|  | 3.13.1 | If either (i) the Project contemplates Work by way of renovations in buildings which will be in use or be occupied during the course of the Work or (ii) the Project involves Work that is adjacent to a structure which is in use or is occupied, then the Contractor shall, without in any way limiting its responsibilities under this Contract, take all reasonable steps to avoid interference with fire exits, building access and egress, continuity of electrical power and all other utilities, to suppress dust and noise and to avoid conditions likely to propagate mould or fungus of any kind and all other steps reasonably necessary to promote and maintain the safe and comfortable usability of such structures or adjacent structures by their users and occupants. |
|  | GC 3.14 | CONTRACTOR STANDARD OF CARE |
|  | 3.14.1 | In performing this Contract, the Contractor shall exercise the degree of care, skill and diligence that would normally be exercised by an experienced, skilled and prudent contractor supplying similar construction services on similar projects. The Contractor acknowledges and agrees that throughout this Contract, the Contractor’s obligations, duties and responsibilities shall be judged, evaluated and interpreted in accordance with this standard. The Contractor shall exercise the same standard of care in respect of any Products, personnel (including any Subcontractors or Suppliers) or procedures which it may recommend to the Owner or employ on the Project. |
|  | GC 3.15 | USE OF PERMANENT EQUIPMENT OR SYSTEMS |
|  | 3.15.1 | In the sole discretion of the Owner (with prior satisfactory arrangements to, and with the prior written approval of the Owner), the Contractor may be permitted to use elements of the Project systems including the elevator, mechanical and electrical systems or equipment comprising a permanent part of the Work, for the purpose of providing conveyance, heat or power to Project during the final stages of construction. In such event, and before the issuance of the certificate of Substantial Performance of the Work, the Contractor shall clean, rehabilitate and make good as new condition to the satisfaction of the Owner and Consultant, such systems and equipment as it had been permitted to use. The Contractor shall pay any and all costs associated with such cleaning, rehabilitation and making good, including the cost of any Owner provided utilities. |
|  | GC 3.16 | SUPPLIER CODE OF CONDUCT |
|  | 3.16.1 | The University of Victoria Supplier Code of Conduct (“SCoC”), which is available at https://www.uvic.ca/purchasing/assets/docs/uvicsuppliercodeofconduct.pdf or upon request from the Owner, is hereby incorporated by reference and forms part of these General Conditions. The Contractor agrees that it shall fully comply with the SCoC. If the Contractor is not in compliance with the SCoC, the Owner may, without prejudice to any other right or remedy the Owner may have, give the Contractor Notice in Writing, containing particulars of the default including references to applicable provisions of the Contract. The Contractor will have the time specified in the foregoing Notice in Writing to propose a remediation plan for approval by the Owner, which remediation plan will include the time required by the Contractor to become compliant with the SCoC. Notwithstanding any other provisions contained in this Contract, if (i) no remediation plan is submitted as required, (ii) the Owner does not approve a remediation plan within 14 days of receipt of the Contractor’s initial proposed remediation plan or (iii) the Contractor fails to achieve the Contractor’s remediation plan, then the Owner may immediately terminate this Contract on Notice in Writing to the Contractor.” |
|  | GC 4.1.2 | Insert the following at the end of paragraph 4.1.2: |
|  |  | “Unless expressly specified, none of the Work included in the Drawings and Specifications is intended to be paid for by the cash allowances. The cash allowances are for the Owner’s use and at the Owner’s sole discretion.” |
|  | GC 4.1.8 | Insert the following new paragraph after paragraph 4.1.7: |
|  | “4.1.8 | The Owner may direct the Contractor to conduct a competitive procurement process for any work, materials or Products for which payment is to be made from a cash allowance.” |
|  | GC 4.2.1 | Insert the following at the end of paragraph 4.2.1: “The contingency allowance is for the Owner’s use and at the Owner’s sole discretion.” |
|  | GC 5.1 | Delete GC 5.1 – FINANCING INFORMATION REQUIRED OF THE OWNER in its entirety and substitute “Intentionally blank”. |
|  | GC 5.2.2 | In paragraph 5.2.2 delete “which is the last day of the month” and substitute with “which is the twenty-fifth (25th) day of the month”. |
|  | GC 5.2.4 | Insert the following at the end of paragraph 5.2.4: |
|  |  | “The schedule of values shall be prepared in such a manner that each major item of Work and each subcontracted item of Work is shown as a separate line item and, in the case of each subcontract, shall accurately represent the subcontract price, and the Consultant and the Owner shall be entitled to rely on same. Separate amounts shall be shown for mobilization and start-up, continuing expenses and project close-out. The Contractor acknowledges that no application for payment will be deemed to be received by the Consultant or the Owner under paragraph 5.3.1 until the schedule of values is accepted and approved in writing by the Owner.” |
|  | GC 5.2.7 | Delete 5.2.7 in its entirety and substitute the following new paragraph: |
|  | “5.2.7 | Applications for payment shall be submitted to the Consultant, together with the applicable statutory declaration(s) (to be on the latest version of the CCDC 9A or CCDC 9B forms, as applicable) and such other documents as are requested by the Consultant or the Owner. Applications for payment for changes in the Work shall not be valid or become due and payable without a written Change Order and/or Change Directive issued by the Consultant (and signed by the Owner). If the application for payment is received after this date or not in the required format, it will not be processed for payment until the subsequent month.” |
|  | GC 5.2.8 | Delete 5.2.8 in its entirety and substitute the following new paragraphs: |
|  | “5.2.8 | Before the Contractor submits each application for payment, the Contractor shall document the progress of the Work on site to establish the value of the Work performed. The Consultant or the Owner may attend at the site to verify the progress of the Work and the value of the Work performed as documented by the Contractor. |
|  | 5.2.9 | Each Contractor’s application for payment shall be accompanied by the following information: .1 a statement based on the schedule of values; .2 supporting documentation related to the schedule of values including invoices, receipts, payrolls and equipment rental schedules; .3 a sworn statutory declaration (or declarations) as specified in paragraph 5.2.7; .4 if requested: (1) the names of Subcontractors and Suppliers to be paid by the Contractor and the amount to be paid to each; (2) a sworn statutory declaration from Subcontractors and Suppliers, in form and substance satisfactory to the Consultant and the Owner; (3) a release and waiver applicable Subcontractors and Suppliers, in form and substance satisfactory to the Consultant and the Owner; .5 the total amount of expenditures to date and the total estimated expenditures to be made for the remaining balance of the Work; .6 a letter of good standing with Workers Compensation Board / WorkSafe BC; .7 evidence as the Consultant may direct in accordance with paragraph 5.2.12; and .8 any additional supporting information as the Owner or Consultant may direct. |
|  | 5.2.10 | Upon receipt of a written request from the Owner or Consultant, the Contractor shall also make available to the Owner or Consultant the Contractor’s files setting forth the addresses of all Subcontractors, labourers and Products Suppliers and the names of all labourers involved in the Work, and Consultant and Owner shall have the right to make and retain copies of the same. |
|  | 5.2.11 | The Contractor acknowledges and agrees that no application for payment shall be considered complete or received for the purposes of the Contract until all required supporting documentation is submitted, as determined by the Consultant. |
|  | 5.2.12 | No payment shall be claimed for Products delivered to the Place of the Work, or elsewhere, prior to their incorporation into the Work without the Consultant’s (or the Owner’s) prior consent to the delivery and such evidence as the Consultant may reasonably require to establish the value and delivery of such Products.” |
|  | GC 5.3.1 | Delete paragraph 5.3.1 in its entirety and substitute the following: |
|  | “5.3.1 | After receipt by the Consultant and the Owner of a completed application for payment submitted by the Contractor in accordance with GC 5.2 – APPLICATIONS FOR PAYMENT: .1 subject to paragraph 5.3.2, the Consultant will issue to the Owner and copy the Contractor, no later than 10 calendar days after the receipt of the application for payment, a certificate for payment in the amount applied for, or in such other amount as the Consultant determines to be properly due. If the Consultant certifies a different amount, or rejects the application or part thereof, the Owner shall promptly issue a written notice to the Contractor giving reasons for the revision or rejection, such written notice to be in compliance with Payment Legislation; and .2 the Owner shall make payment to the Contractor on account as provided in Article A-5 of the Agreement – PAYMENT on or before 28 calendar days following the receipt by the Owner and the Consultant of the completed application for payment and in any event, in compliance with Payment Legislation. |
|  | 5.3.2 | Subject to the requirements of any Payment Legislation, the Consultant or the Owner may decline to approve an application for payment and may withhold a certificate for payment in whole or in part, if in the Consultant’s reasonable opinion, the Work has not progressed to the point indicated or the quality of the Work is not in accordance with the Contract Documents. Subject to the requirements of any Payment Legislation, the Consultant or the Owner may also decline to approve any application for payment or, because of subsequently discovered evidence, testing or subsequent inspections, the Consultant or the Owner may provide for a withholding of funds to offset a previous payment made pursuant to any certificate for payment previously issued or the Owner may refuse to make payment, to such extent as may be necessary in its opinion to protect the Owner from loss because of: .1 defective work not remedied; .2 third party claims filed or reasonable evidence indicating possible filing of such claims; .3 failure of the Contractor to make payments promptly to Subcontractors, Suppliers or for labour, Products or equipment; .4 damage to work of Other Contractors or property adjacent to the Place of the Work; or .5 unsatisfactory prosecution of the Work by the Contractor, any Subcontractor or Supplier. |
|  | 5.3.3 | No payment made by the Owner under this Contract nor any partial or entire use or occupancy of the Work by the Owner shall constitute either (a) an acceptance of any portion of the Work or any Products which are not in accordance with the requirements of the Contract Documents, or (b) a waiver of any claim the Owner may have against the Contractor. |
|  | 5.3.4 | Subject to the requirements of any Payment Legislation, if the Consultant (or the Owner) has reasonable grounds for believing that any amount included in previous applications for payment of the Contractor or paid to the Contractor by the Owner has not been paid to Subcontractors, Suppliers or other third parties to whom such amounts are due, then the Consultant (or the Owner) may withhold payment in respect of such amount from any future payments until satisfactory evidence of payment is provided to the Consultant (and the Owner) by the Contractor.” |
|  | GC 5.4 | Delete General Condition 5.4 in its entirety and substitute the following: |
|  | “GC 5.4 | SUBSTANTIAL PERFORMANCE OF THE WORK AND PAYMENT OF HOLDBACK |
|  | 5.4.1 | When the Contractor considers that the Work is substantially performed, the Contractor shall deliver to the Consultant and to the Owner a comprehensive list of items to be completed or corrected, together with a written application for review. Failure to include an item on the list does not alter the responsibility of the Contractor to complete the Contract. |
|  | 5.4.2 | The Consultant will review the Work to certify or verify the validity of the application for Substantial Performance of the Work and will promptly, and in any event, no later than 10 calendar days after receipt of the Contractors application: .1 advise the Contractor in writing that the Work or the designated portion of the Work is not substantially performed and give reasons why, or .2 state the date of Substantial Performance of the Work or a designated portion of the Work in a certificate and issue a copy of that certificate to each of the Owner and the Contractor. |
|  | 5.4.3 | Immediately following the issuance of the certificate of Substantial Performance of the Work, the Contractor, in consultation with the Consultant, shall establish a reasonable date for finishing the Work and correcting any deficient Work, as applicable. |
|  | 5.4.4 | The Contractor shall give to the Owner a minimum of 45 calendar days advance Notice in Writing that it will request or apply for the certificate of Substantial Performance of the Work. |
|  | 5.4.5 | Subject to paragraph 5.4.6 of GC 5.4 – SUBSTANTIAL PERFORMANCE OF THE WORK AND PAYMENT OF HOLDBACK, prior to making application for Substantial Performance of the Work, the Contractor shall, subject to paragraph 5.4.7, submit to the Consultant the following: .1 letters of assurance for professional design and review from those professionals engaged by the Contractor under the provisions of the Contract, including applicable sealed Shop Drawings; .2 all required manufacturer’s inspections, certifications, guarantees, warranties as specified in the Contract Documents; .3 all maintenance manuals, operating instructions, maintenance and operating tools, replacement parts, samples or materials as specified in the Contract Documents; .4 certificates and correspondence issued by all permit issuing authorities indicating approval of all installations, work and improvements requiring permits; .5 certificates issued by all testing, commissioning, cleaning, inspection authorities and associations as applicable or specified in the Contract Documents; and .6 all required record Drawings and As-Built Drawings and as-installed documents in the form specified in the Contract Documents. |
|  | 5.4.6 | If the Contractor could not have, with all requisite diligence and attention, practicably obtained one or more of the items listed in paragraph 5.4.5 for the time of Substantial Performance of the Work, then delivery of such items may be deferred until the date that is 30 days following Substantial Performance of the Work. |
|  | 5.4.7 | Together with its request or application for the certificate of Substantial Performance of the Work, the Contractor shall provide to the Owner and the Consultant the following: .1 a current clearance letter from Workers' Compensation Board confirming that the Contractor is in good standing with and that all required remittances and assessments have been made to the Workers' Compensation Board; .2 if requested by the Owner or the Consultant, confirmation from any or all of the Subcontractors and Suppliers that they have been paid in full except for holdbacks properly retained; .3 a properly executed Contractor's release in the format prescribed by the Owner or the Consultant, releasing all claims except those for which Notice in Writing has been given to the Owner as contemplated in paragraph 13.2.1.1; .4 a statement compiling and reconciling all Change Orders and Change Directives; .5 a list of all claims and demands for changes and delay, or otherwise for adjustment or reimbursement or any other claims whatsoever, under or in connection with the Contract; and .6 any other documents to be submitted by the Contractor as specified in the Contract or reasonably required by the Owner or the Consultant provided that in relation to record or As-Built Drawings, the Contractor shall submit full and complete record of As-Built Drawings to the Consultant within forty-five (45) days of the issuance of the certificate of Substantial Performance of the Work. |
|  | 5.4.8 | Prior to the Owner making the payment otherwise due to the Contractor at the time of Substantial Performance of the Work, the Owner may require that: .1 the Contractor acknowledges and agrees (in the certificate of Substantial Performance of the Work, or in a separate document, as the Owner prescribes) that the Contractor does not have and will not make any claim for additional compensation for extras, changes or delays or any other claims whatsoever against the Owner in connection with the Contract or the Project or the Work, and that the Contractor agrees that the payment made by the Owner shall be received by the Contractor in full and final settlement of the balance due to the Contractor under the Contract and of any and all claims of the Contractor in connection with the Contract (except only for the Contractor’s claim for any amount expressly held back by the Owner for the list of deficiencies, uncompleted Work or otherwise). Despite any provision in the Contract to the contrary, the time for the Owner to make any payment otherwise due at the time of Substantial Performance of the Work shall be extended until any and all such claims have been settled or resolved; and .2 the Contractor undertakes and agrees (in the certificate of Substantial Performance of the Work, or in a separate document, as the Owner prescribes) to carry out the deficient or defective and incomplete Work within the specific dates set out and agreed upon by the Contractor and the Owner, or reasonably prescribed by the Owner. |
|  | 5.4.9 | Without limiting the Contractor’s obligations pursuant to paragraphs 5.4.7.3 and 5.4.8.1, the Contractor acknowledges and agrees that acceptance by the Contractor of the certificate of Substantial Performance of the Work, or the acceptance of a certificate by a Subcontractor or for any payment due thereunder shall constitute a waiver by either the Contractor, or the Subcontractor, as the case may be, of all claims whatsoever against the Owner under this Contract or any trade contract whether for a change in the Contract Price, extension of Contract Time, or otherwise, except those made in writing prior to the Contractor’s application for payment upon Substantial Performance of the Work and still unsettled. |
|  | 5.4.10 | The Contractor shall conform to all requirements of Applicable Law in force in the jurisdiction of the Place of the Work with respect to providing notice of and publishing a copy of the certificate of Substantial Performance of the Work. Without limiting the foregoing, within seven (7) calendar days of receiving a copy of the certificate of Substantial Performance of the Work signed by the Consultant, the Contractor shall publish a copy of the certificate in a construction trade newspaper and shall provide to the Consultant and the Owner the date of publication and the name of the construction trade newspaper in which the publication occurred. If the Contractor fails to comply with this provision, the Owner may publish a copy of the certificate and charge the Contractor with the costs so incurred. |
|  | 5.4.11 | Deficiency Retention Notwithstanding any provisions contained in the Contract Documents concerning certification and release of monies to the Contractor, the Owner reserves the right to establish a deficiency retention at the time of the review for Substantial Performance of the Work, based on a 200% dollar value of (a) the deficiencies to be corrected, and (b) work to be completed (including the delivery of As-Built Drawings and three (3) copies of the Project maintenance manuals), in each case, as listed by the Consultant (the “Deficiency Retention”). If the Consultant determines, at the time the Consultant issues a final certificate for payment as set out in GC 5.5 – FINAL PAYMENT, that there are still outstanding deficiencies or incomplete work, then the Owner may retain some or all of the Deficiency Retention as required for the Owner to correct the deficiencies or complete the Work. The Deficiency Retention is separate from and in addition to the lien holdback referred to in this Contract. |
|  | 5.4.12 | After the issuance of the certificate of Substantial Performance of the Work, the Contractor shall: .1 submit an application for payment of the holdback amount, .2 submit CCDC 9A ‘Statutory Declaration’ to state that all accounts for labour, subcontracts, Products, Construction Equipment, and other indebtedness which may have been incurred by the Contractor in the Substantial Performance of the Work and for which the Owner might in any way be held responsible have been paid in full, except for amounts properly retained as a holdback or as an identified amount in dispute, .3 when applying for release of a holdback amount, submit a statutory declaration and waiver from each applicable Subcontractor and Supplier (in form and substance satisfactory to the Owner and Consultant and a Workers Compensation Board letter of good standing).” |
|  | 5.4.13 | After the receipt of an application for payment from the Contractor and the documents as provided in paragraph 5.4.12, the Consultant will issue a certificate for payment of the holdback amount. |
|  | 5.4.14 | Subject to the requirements of any Payment Legislation, the lien holdback amount authorized by the certificate for payment of the lien holdback amount is due and payable no later than 10 Working Days following the expiration of the lien holdback period stipulated in the lien legislation applicable to the Place of the Work, provided that no liens have been registered or claimed and no proceedings have been commenced to enforce a lien against the lien holdback amount. The Owner may retain out of the lien holdback amount any sums required by Applicable Law to satisfy any liens against the Work or, if permitted by the lien legislation applicable to the Place of the Work, other third party monetary claims against the Contractor which are enforceable against the Owner. Prior to applying for the release of lien holdback funds, the Contractor shall have submitted the following documents, each in a form satisfactory to the Consultant and the Owner and dated after the expiration of the applicable lien period from the issuance date of the certificate of Substantial Performance of the Work issued by the Consultant: .1 a declaration from the Contractor to the Owner, in a form satisfactory to the Owner, to the effect that: (1) no lien associated with the Work exists against the Owner’s property and the Work; and (2) no action has been commenced in connection with any holdback funds related to the Work; .2 statutory declarations in the forms satisfactory to the Owner, verifying that all liabilities incurred by the Contractor and its Subcontractors and Suppliers in carrying out the Work have been paid and there are no outstanding liens, garnishes, attachments, or claims relating to the Work; .3 a certificate of clearance certifying the Contractor’s compliance with the requirements of the Workers Compensation Act (British Columbia) including any payments due thereunder; .4 all warranties required under the provision of this Contract, whether originating from the Contractor, Subcontractors or Suppliers; and .5 a release stating that the Contractor has no further claims against the Owner in respect to the Contract. |
|  | 5.4.15 | Where, upon application by the Contractor, the Consultant has certified that the work of a Subcontractor or Supplier has been performed prior to Substantial Performance of the Work, the Owner shall, subject to the requirements of any Payment Legislation, pay the Contractor the holdback amount retained for such subcontract work, or the Products supplied by such Supplier, no later than 10 Working Days following the expiration of the holdback period for such work stipulated in the lien legislation applicable to the Place of the Work. The Owner may retain out of the holdback amount any sums required by Applicable Law to satisfy any liens against the Work or, if permitted by the lien legislation applicable to the Place of the Work, other third party monetary claims against the Contractor which are enforceable against the Owner. Notwithstanding the foregoing, and notwithstanding the wording of such certificates, the Contractor shall ensure that such subcontract work or Products are protected pending the issuance of a final certificate for payment and be responsible for the correction of defects or work not performed regardless of whether or not such was apparent when such certificates were issued. |
|  | 5.4.16 | For release of the holdback on Work performed by a Subcontractor pursuant to a subcontract which is 100% complete, after the expiry of the holdback period defined in the lien legislation applicable to the Place of the Work, the Contractor shall make an application prior to final payment by written request for a review to determine the date of completion of such subcontract and shall submit such supporting material as the Consultant may in his discretion require, and may include statutory declarations from such persons and dealing with such matters as the Consultant requires. Such material shall in any event include: .1 a description of the scope of the Work; .2 Workplace Safety & Compensation Board clearance certificate for the Contractor, the Subcontractor concerned, and any other Subcontractors and Suppliers who have provided any services to the Subcontractor; .3 a statutory declaration and waiver by an officer of the Subcontractor, in form and substance satisfactory to the Owner; .4 the Contractor’s written acknowledgement to the Owner that the requirements of the Contract Documents will not be altered by early release of the holdback in respect of such completed subcontract; and .5 confirmation by the bonding company that it has been notified of the intent to claim early release of holdback and does not object. An application for progressive release of holdback will not be considered complete until all related documentation required for the Consultant’s review is received, including those requirements in GC 5.2.9.” |
|  | GC 5.5.1 | Delete paragraph 5.5.1 in its entirety and substitute the following: |
|  | “5.5.1 | When the Contractor considers that the Work is completed, as defined in the lien legislation applicable to the Place of the Work or if such definition does not exist, in accordance with other Applicable Law, industry practice or provisions which may be agreed to between the parties, the Contractor shall submit an application for final payment. The Contractor’s application for final payment shall be accompanied by any documents or materials not yet delivered pursuant to paragraph 5.4.6 of GC 5.4 – SUBSTANTIAL PERFORMANCE OF THE WORK AND PAYMENT OF HOLDBACK, together with: .1 complete and final As-Built Drawings; .2 the Contractor’s written request for release of the Deficiency Retention, including a statement that no written notices of lien have been received by it; .3 a sworn statutory declaration (to be on the latest version of CCDC 9A or CCDC 9B forms, as applicable); .4 a written statement that the Work has been performed to the requirements of the Contract Documents, and itemizing approved changes in the Work and the Consultant’s written instructions and modifications indicated by the Governmental Authorities having jurisdiction; .5 the evidence of workers’ compensation compliance required by paragraph 10.4.1 of GC 10.4 – WORKERS’ COMPENSATION; .6 a certificate of publication in accordance with paragraph 5.4.10 of GC 5.4 – SUBSTANTIAL PERFORMANCE OF THE WORK AND PAYMENT OF HOLDBACK; .7 such other materials or documentation as may be required to be submitted under the Contract Documents; and .8 any other requirement for an application for payment set out in GC 5.2 – APPLICATION FOR PAYMENT. The Work shall be deemed not to be completed until all of the aforementioned documents have been delivered.” |
|  | GC 5.5.4 | In paragraph 5.5.4 delete “5 calendar days” and insert “28 calendar days”. |
|  | GC 5.5.4 | Insert the following new paragraphs following paragraph 5.5.4: |
|  | “5.5.5 | Subject to the requirements of any Payment Legislation: .1 no partial or progressive payments of the Deficiency Retention amounts will be considered; and .2 no application for payment for final payment will be accepted, until all incomplete and deficient work has been completed to the satisfaction of the Owner and the Consultant. |
|  | 5.5.6 | If the defective or incomplete work is not corrected or completed by the Contractor within the reasonable time established pursuant to paragraph 5.4.3, then the Owner may have all or a portion of the deficient or defective work corrected or completed by whatever means may be expedient and the Owner may deduct and set off all associated costs against amounts otherwise owed or payable to the Contractor. |
|  | 5.5.7 | The issuance of a final certificate for payment or the payment of lien holdback and Deficiency Retention amounts shall not relieve the Contractor's responsibility for correction of any other deficiencies or incomplete items, at no additional cost to the Owner, that may not have been included in the list of deficient items or which may not have been apparent during the review carried out pursuant to GC 5.4 – SUBSTANTIAL PERFORMANCE OF THE WORK AND PAYMENT OF HOLDBACK.” |
|  | GC 5.6.1 | Insert the following as a new paragraph after paragraph 5.6.1: |
|  | “5.6.2 | Without restricting any right of set-off given or implied by Applicable Law, the Owner may set-off against any amounts payable under the Contract Documents to the Contractor any amount, including without limitation expenses and damages, owing by the Contractor to the Owner.” |
|  | GC 5.8 | Insert the following new General Condition GC 5.8 – LIENS: |
|  | “GC 5.8 | LIENS |
|  | 5.8.1 | The Contractor shall promptly give the Owner notice (in writing) of any encumbrance or lien of any kind or nature placed upon or obtained against the property of the Owner, the Place of the Work or the Project in, or as a result of, any act or omission of the Contractor, its Subcontractors, Suppliers, or any servant(s), agent(s) or employee(s) of the Contractor or any of its Subcontractors or Suppliers. |
|  | 5.8.2 | If an encumbrance or lien is registered against the property of the Owner, the Place of the Work or the Project in, as a result of, any act or omission of the Contractor, its Subcontractors or Suppliers, or any servant(s), agent(s) or employee(s) of the Contractor or any of its Subcontractors or Suppliers, then the Contractor shall, at its own expense: .1 within 10 calendar days, ensure that any and all encumbrances or liens and certificates of pending litigation or actions are discharged, released, dismissed or vacated by the posting of security or otherwise; and .2 in the case of written notices of encumbrances or lien, ensure that such notices are withdrawn, in writing. |
|  | 5.8.3 | In the event that the Contractor fails to comply with the requirements of paragraph 5.8.2, the Owner may (but shall not be obliged to) discharge, release or vacate such encumbrance or lien without notice to the Contractor and shall be entitled to set-off and deduct from any amount owing to the Contractor, all costs and expenses, including the costs of posting security and all legal fees and disbursements associated with discharging, releasing, dismissing or vacating the encumbrance or lien, or certificate of pending litigation or action, and defending any action relating to such encumbrance or lien. If there is no amount owing by the Owner to the Contractor or to the extent the Owner’s costs and expenses exceed the amount owed by the Owner to the Contractor, then the Contractor shall reimburse the Owner for all of the said costs and associated expenses.” |
|  | GC 6.1.2 | Delete paragraph 6.1.2 in its entirety and substitute the following: |
|  | “6.1.2 | No changes in the Work shall proceed without a written Change Order or Change Directive signed by the Owner and no claim for any change in the Contract Price or for any extension or alteration of the Contract Time shall be valid except as shown on the Change Order or Change Directive, as the case may be. No course of conduct or dealing between the parties, no express or implied acceptance of alterations or additions to the Work and no claim that the Owner has been unjustly enriched by any alteration or addition to the Work, whether in fact there is any such unjust enrichment or not, shall be the basis of a claim for payment under this Contract or any extension of the Contract Time without a Change Order or Change Directive. This requirement is of the essence and it is the express intention of the parties that any claims by the Contractor for a change in the Contract Price and/or Contract Time shall be barred unless there has been strict compliance with PART 6 - CHANGES IN THE WORK. |
|  | 6.1.3 | If any change or deviation in, or omission from the Work is made by which the amount of Work to be done is decreased, or if the whole or a portion of the Work is dispensed with, no compensation is claimable by the Contractor or any Subcontractor for any Indirect Loss. |
|  | 6.1.4 | The Contractor agrees that changes resulting from construction coordination including but not limited to site surface conditions, site coordination, Subcontractor and Supplier coordination are included in the Contract Price and shall not entitle the Contractor to claim additional amounts in excess of the Contract Price.” |
|  | GC 6.2.2 | Insert the following new paragraphs after paragraph 6.2.2: |
|  | “6.2.3 | With respect to the evaluation of changes in the Work, the paragraph 6.2.4 description of mark-ups for all office and site related overhead (including all necessary management, estimating, administration, supervision, insurance, bonding, financing, warranty, general account items, continuing expense, unloading, unpacking, disposing of packing materials, cleaning, hoisting, clean-up, small tools, as-built drawings, job safety and all other related indirect work) and profit shall apply. |
|  | 6.2.4 | For each change in the Work, the Contract Price shall be increased by the net cost of that change in the Work, plus the following permitted mark-ups for all overhead and profit: .1 the Contractor’s mark-up for Work performed by the Contractor’s own forces: 15% of the net cost of such Work performed by the Contractor’s own forces; .2 the Contractor’s mark-up for Work performed by Subcontractors or Suppliers: 10% of the net cost of such Work performed by the Subcontractors or Suppliers; and .3 a Subcontractor’s or Suppliers mark-up for Work performed by a Subcontractor’s or Suppliers own forces: 10% of the net cost of such Work performed by the Subcontractor’s or Supplier’s own forces. For greater certainty, a Subcontractor or Supplier (the “First Tier Contractor”) (i) will only be entitled to charge a mark-up for Work performed by the First Tier Contractor’s own forces, and (ii) will not be entitled to charge a markup-up on Work performed by a Subcontractor or Supplier of the First Tier Contractor.” |
|  | GC 6.3 | Delete GC 6.3 – CHANGE DIRECTIVE in its entirety and substitute the following: |
|  | “GC 6.3 | CHANGE DIRECTIVE |
|  | 6.3.1 | When a change in the Work is proposed or required, the Consultant will provide the Contractor with a written description of the proposed change to the Work. If, in the Contractor’s estimate, the proposed work is of a time sensitive nature and in order to mitigate unnecessary charges which may occur should the change to the Work not be approved immediately and/or to avoid any delay in the schedule, the Contractor shall immediately notify the Consultant. If the Consultant agrees with the Contractor’s assessment, the Consultant will immediately notify the Owner and include all relevant information surrounding the request for a Change Directive. If the Owner agrees, the Consultant will immediately issue a Change Directive. All work to be done on a Change Directive will be done on a time and materials basis. The Contractor will provide to the Consultant daily time sheets listing the hours spent by each sub-trade assigned to the task(s) and will also provide invoices for any materials procured specifically for this work and/ or incorporated into the Work. If requested by the Owner, the Contractor will, as soon as practicable after commencing the work contemplated by the Change Directive, provide a fixed price quotation for the change in accordance with paragraph 6.2.1 which, when recommended by the Consultant and accepted by the Owner, shall be deemed the total cost of the change in the Work. |
|  | 6.3.2 | Submission of quotations, including markups, on any work requested via Change Directive shall be in accordance with GC 6.2 – CHANGE ORDER.” |
|  | GC 6.4.1 | Delete paragraph 6.4.1 in its entirety and substitute the following: |
|  | “6.4.1 | The Contractor: .1 confirms that, prior to submitting its bid proposal in relation to the Project, it carefully investigated the Place of the Work using the degree of care and skill described in paragraph 3.14.1 in relation to such investigation. .2 hereby acknowledges and agrees that it will not be entitled to make any claim in connection with conditions which could reasonably have been ascertained by such investigation undertaken prior to the award of the Contract.” |
|  | GC 6.4.2 | At the beginning of paragraph 6.4.2, insert the following as a new first sentence: |
|  |  | “Subject to paragraph 6.4.1, if the Contractor considers that the conditions of the Place of the Work either (i) differ materially from those reasonably anticipated, (ii) differ materially from those indicated in the Contract Documents, or (iii) were concealed from discovery notwithstanding the conduct of the investigation described in paragraph 6.4.1, then the Contractor shall provide the Owner and the Consultant Notice in Writing no later than five (5) Working Days after becoming aware of such condition.” |
|  | GC 6.4.3 | Delete paragraph 6.4.3 in its entirety and substitute the following: |
|  | “6.4.3 | If the Consultant makes a finding pursuant to paragraph 6.4.2 that no change in the Contract Price or the Contract Time is justified, the Consultant shall report in writing the reasons for this finding to the Owner and the Contractor.” |
|  | GC 6.4.4 | Delete paragraph 6.4.4 in its entirety and substitute the following: |
|  | “6.4.4 | If such concealed or unknown conditions relate to Hazardous Substances and materials, artifacts and fossils, or mould, the parties will be governed by the provisions of GC 9.2 - HAZARDOUS SUBSTANCES, GC 9.3 – ARTIFACTS AND FOSSILS and GC 9.5 — MOULD.” |
|  | GC 6.5.1 | Delete paragraph 6.5.1 in its entirety and substitute the following: |
|  | “6.5.1 | If (i) the Contractor is delayed in the performance of the Work by an action or omission of the Owner or Consultant or anyone employed or engaged by them directly or indirectly (other than the Contractor, the Subcontractors, Suppliers or anyone employed or engaged by them directly or indirectly) contrary to the provisions of the Contract Documents, and (ii) the Contractor has given the Owner and Consultant a Notice in Writing in a timely fashion of the action or omission that has given rise to such delay, then (1) the Contract Time shall be extended for such reasonable time as the Consultant determines, and (2) the Contractor shall be reimbursed by the Owner for reasonable costs incurred by the Contractor as the result of such delay (excluding any Indirect Costs). In the event of a dispute as to the amount of such costs such dispute shall be resolved in accordance with Part 8 of the General Conditions - DISPUTE RESOLUTION.” |
|  | GC 6.5.2 | Revise paragraph 6.5.2 by, (a) deleting the words “in consultation with the Contractor” at the end of the first sentence; and (b) deleting the last sentence and replacing it with the following: “The Contractor shall be reimbursed by the Owner for reasonable costs incurred by the Contractor as the result of such delay (excluding any Indirect Costs) provided that such delay did not result from the act or omission of the Contractor or anyone employed or engaged by Contractor directly or indirectly. In the event of a dispute as to the amount of such costs such dispute shall be resolved in accordance with Part 8 of the General Conditions - DISPUTE RESOLUTION.” |
|  | GC 6.5.3 | Delete paragraph 6.5.3 in its entirety and substitute the following: |
|  | “6.5.3 | If the Contractor is delayed in the performance of the Work as a result of Force Majeure, then Contract Time shall be extended for such reasonable time as the Consultant may recommend. The Contractor shall not be entitled to any additional compensation as a result of such Force Majeure event or the delay occasioned thereby and shall not be compensated for any additional costs, directly or indirectly arising as a result of such Force Majeure event or the delay occasioned thereby (including, without limiting the generality of the foregoing, any additional costs arising out of winter construction). No controversy or dispute between in relation to such delay shall constitute a cause for stoppage of the performance of the Contractor’s obligations or services or for a delay or extension.” |
|  | GC 6.5.4 | Delete paragraph 6.5.4 in its entirety and substitute the following: |
|  | “6.5.4 | No extension shall be made for delay unless Notice in Writing of the cause of the delay is given to the Consultant and the Owner not later than 10 Working Days after the commencement of the delay. In the case of a continuing cause of delay only one Notice in Writing shall be necessary. A notice of claim with respect to any delay shall indicate the reasons for such delay and the best estimate of the Contractor as to its duration and the effect upon the Contract Time, and such other supporting documentation as may be required by the Consultant and the Owner (in their discretion). Upon termination of the circumstances giving rise to the delay, the Contractor shall give to the Owner and Consultant a Notice in Writing of the termination of the delay.” |
|  | GC 6.5.5 | Insert the following new paragraphs after paragraph 6.5.5: |
|  | “6.5.6 | No extension shall be made for delay arising from strikes, lock outs and other industrial disturbances that is decreed for its members by a recognized contractor’s association of which the Contractor is a member or to which the Contractor is otherwise bound if the Contractor, before entering into this Contract or commencing the Work, had or should have had knowledge that or reasonable grounds for believing that the Work would be delayed by such a labour dispute and did not so inform the Owner and Consultant in writing. |
|  | 6.5.7 | If there is a delay in the performance of any portion of the Work, the Contractor shall take commercially reasonable efforts to mitigate the consequences of such delay including the rescheduling of the Work and the Contractor’s failure to mitigate shall be taken into account any extension to the Contract Time. |
|  | 6.5.8 | Subject to Applicable Law, the Owner or Consultant may order the Work to proceed on a two or three eight-hour shift basis if it deems this necessary to speed up the Work, or it may order any Work to be carried out in whole or in part at night. No Work, however, shall be undertaken at night without the consent in writing of the Owner or Consultant. If, at the time of such order: .1 the progress of the Work has been delayed and the Contractor is not compliant with the Time Schedule, then the Contractor shall have no claim for extra compensation in respect thereof; .2 the progress of the Work has not been delayed and the Contractor is compliant with the Time Schedule, then the additional net cost of such additional time (less any savings realized by the Contractor through the earlier completion of the Work) shall be chargeable to the Owner. |
|  | 6.5.9 | Any adjustment to the Contract Time required as a result of GC 6.5 - DELAYS shall be made as provided in GC 6.1 - OWNER’S RIGHT TO MAKE CHANGES, GC 6.2 - CHANGE ORDER and GC 6.3 - CHANGE DIRECTIVE. |
|  | 6.5.10 | If the Consultant determines that the Contractor is delayed in the performance of the Work, or any part thereof, by an action or omission of the Contractor (or anyone employed or engaged by the Contractor directly or indirectly) or by any cause within the Contractor’s control (including, without limitation, by a stop work order issued by a court or other Governmental Authority as a result of an act or fault of the Contractor (or anyone employed or engaged by the Contractor directly or indirectly)) and the Contract Time is affected, then: .1 the Consultant will promptly give Notice in Writing of such determination to the Owner and the Contractor; .2 the Contractor shall accelerate the Work as required to meet the Contract Time; .3 the Contractor shall then promptly give the Owner and the Consultant Notice in Writing of specific changes to the construction scheduling and construction processes the Contractor will implement to accelerate the Work; .4 the Contractor shall not be entitled to payment for costs to accelerate the Work to meet the Contract Time; and .5 the Owner shall be reimbursed by the Contractor for reasonable costs incurred by the Owner as the result of such delay. |
|  | 6.5.11 | If the Consultant determines that the Work has not been sufficiently accelerated to mitigate the delay, then the Contract Time may be extended for such reasonable time as the Consultant may determine. The Owner shall be reimbursed by the Contractor for all reasonable costs incurred by the Owner as the result of such delay, including all services required by the Owner from the Consultant as a result of such delay by the Contractor and, in particular, the cost of the Consultant’s services during the period between the date of Substantial Performance of the Work stated in Article A-1 herein as the same may be extended through the provision of these General Conditions and any later actual or date of Substantial Performance of the Work achieved by the Contractor. In the event of a dispute as to extension of time or the amount of such costs such dispute shall be resolved in accordance with Part 8 of the General Conditions - DISPUTE RESOLUTION. |
|  | 6.5.12 | During any delays in the performance of the Work as set out in GC 6.5 – DELAYS, the Contractor shall maintain adequate surveillance of the Work and undertake such maintenance and protection of the Work as may be reasonable to maintain safety and when possible to protect Products already installed in the Work or delivered to the Place of the Work.” |
|  | GC 6.6.1 | In paragraph 6.6.1, insert the following after the word “Consultant”: “in no case more than 10 Working Days from the event or series of events giving rise to the claim.” |
|  | GC 7.1.1 | In paragraph 7.1.1, add the words “commits an act of bankruptcy,” after the word “bankrupt,”. In paragraph 7.1.1, add the words “or a proposal” after the word “assignment” in paragraph 7.1.1. |
|  | GC 7.1.5 | Delete paragraph 7.1.5 in its entirety and substitute the following: |
|  | “7.1.5 | If the Owner terminates the Contractor’s right to continue with the Work in whole or in part or terminates the Contract, as provided in paragraphs 7.1.1, 7.1.4 or elsewhere in the Contract, the Owner shall be entitled to: .1 take possession of the Work and Products at the Place of the Work; subject to the rights of third parties, utilize the Construction Equipment at the Place of the Work; finish the Work by whatever method the Owner may consider expedient, but without undue delay or expense, and .2 withhold further payment to the Contractor until a final certificate for payment is issued, and .3 charge the Contractor an amount equal to the cost of finishing the Work as certified by the Consultant, including compensation to the Consultant for the Consultant’s additional services and a reasonable allowance as determined by the Consultant to cover the cost of corrections to work performed by the Contractor that may be required under GC – 12.3 WARRANTY, and .4 on expiry of the warranty period, charge the Contractor the amount by which the cost of corrections to the Contractor’s work under GC 12.3 - WARRANTY exceeds the allowance provided for such corrections.” |
|  | GC 7.1.6 | Insert the following new paragraphs after paragraph 7.1.6: |
|  | “7.1.7 | For greater certainty, but without intending to limit the circumstances in which notice of default might be given, the Owner will be entitled to give the Contractor Notice in Writing that the Contractor is in default pursuant to paragraph 7.1.2, and to instruct the Contractor to correct the default as set out therein, upon the happening of any of the following: .1 if the Contractor fails to make prompt payment to its Subcontractors and Suppliers; .2 if Work of the Contractor is rejected and the Contractor fails to promptly correct same; .3 if the Contractor has made an assignment of the Contract without the required consent of the Owner; .4 if the Contractor abandons the Work; .5 if the Contractor fails to provide or maintain the bonds or contract security required; .6 if the Contractor fails to carry and maintain required insurance; .7 if the Contractor fails to discharge builders liens when required to do so; .8 if in the reasonable determination of the Consultant the Contractor does not have sufficient workforce, Products or Construction Equipment at the Place of the Work or otherwise is not meeting or will not meet the requirements of the construction schedule, including the requirement to meet important milestone dates from time to time designated by the Owner acting reasonably; and .9 if the Contractor fails to take steps satisfactory to the Consultant or Owner to expedite the performance of the Work or fails to provide a Recovery Schedule acceptable in form and content to the Consultant or Owner, or fails to provide documents requested by the Consultant or Owner to confirm adherence to a Recovery Schedule. |
|  | “7.1.8 | Suspension .1 The Owner may instruct the Contractor to suspend the performance of the Work (or any part thereof) for either a specified or unspecified period by issuing the Contractor with a written notice (“Notice of Suspension”). .2 On receipt of a Notice of Suspension the Contractor shall cease all operations in performance of the Work or identified part thereof except such Work as may be necessary for the protection or safety of Work completed at the time of suspension as directed by the Consultant. .3 During the period of suspension, the Contractor shall remain responsible for the Work then in place, the materials and plant, in each case, to the same extent as if no suspension had occurred. No costs shall be invoiced to the Owner during the period of the suspension. The Owner will compensate the Contractor for reasonable costs and expenses sustained by the Contractor as a result of the suspension provided that the Owner shall not be liable for any Indirect Loss. The Contractor shall make every effort to mitigate these costs and expenses to the Owner. .4 If the suspension is sixty (60) days or less, the Contractor shall resume the performance of the Work within five (5) days following receipt of notification to resume by the Owner. If the suspension exceeds sixty (60) days, no Work will be resumed prior to the Contractor and the Owner having agreed upon the resumption terms and conditions. .5 The Contractor shall not, during the period of suspension, remove from the Place of the Work any part of the Work or any materials, plant or products without the written consent of the Owner. |
|  | 7.1.9 | Termination by Owner for Convenience .1 At any time, the Owner may, for convenience and without cause, terminate the Contract or terminate the Contractor’s right to continue with the Work (or portions thereof) by giving a written notice (such notice, a “Notice of Termination”) to the Contractor. .2 On receipt of a Notice of Termination the Contractor will cease all operations in performance of the Work except such work as may be necessary for the protection or safety of Work completed at the time of termination as directed by the Consultant. .3 The Owner will pay the Contractor and the Contractor will accept in full and final settlement of all monies owing under the Contract an amount based on the Work satisfactorily completed and materials (including any Products) delivered to the Place of the Work but not incorporated into the Work, together with any other unavoidable direct costs incurred by the Contractor as a result of such termination provided that the Owner shall not be liable for any Indirect Loss. The Contractor shall make every effort to mitigate these costs and expenses to the Owner. .4 Title to any materials (including any Products) delivered to the Place of the Work shall transfer to the Owner and the Contractor shall take all steps reasonably required, including the execution of any documents, to protect the Owner’s title and interest in such materials (including any Products).” |
|  | GC 7.2.2 | In paragraph 7.2.2, delete “20 Working Days” and replace with “90 days”. |
|  | GC 7.2.3 | Delete paragraph 7.2.3 in its entirety and substitute the following: |
|  | “7.2.3 | The Contractor may give Notice in Writing to the Owner, with a copy to the Consultant, that the Owner is in default of the Owner’s contractual obligations if: .1 Intentionally blank; .2 the Consultant fails to issue a certificate as provided in GC 5.3 – PAYMENT; .3 the Owner fails to pay the Contractor when due the amounts certified by the Consultant or awarded by arbitration or court, except where the Owner has a bona fide claim for set off; or .4 the Owner violates its obligations to the Contractor pursuant to the Contract to a substantial degree and the Consultant confirms by written statement to the Contractor that sufficient cause exists.” |
|  | GC 8.1.2 | Delete paragraph 8.1.2 in its entirety and substitute the following: |
|  | “8.1.2 | If a dispute arises under the Contract in respect of a matter in which the Consultant has no authority under the Contract to make a finding, the procedures set out in paragraph 8.1.3 and paragraphs 8.3.2 to 8.3.4 of GC 8.3 – NEGOTIATION, MEDIATION AND ARBITRATION, and in GC 8.4 – RETENTION OF RIGHTS apply to that dispute with the necessary changes to detail as may be required.” |
|  | GC 8.3 | Delete GC 8.3 – NEGOTIATION, MEDIATION AND ARBITRATION in its entirety and substitute the following: |
|  | “GC 8.3 | NEGOTIATION, MEDIATION AND ARBITRATION |
|  | 8.3.1 | A party shall be conclusively deemed to have accepted a finding of the Consultant under GC 2.2 – ROLE OF THE CONSULTANT and to have expressly waived and released the other party from any claims in respect of the particular matter dealt with in that finding unless, within 15 Working Days after receipt of that finding, the party sends a Notice in Writing of dispute to the other party and to the Consultant, which contains the particulars of the matter in dispute and the relevant provisions of the Contract Documents. The responding party shall send a Notice in Writing of reply to the dispute within 10 Working Days after receipt of such Notice in Writing setting out particulars of this response and any relevant provisions of the Contract Documents. |
|  | 8.3.2 | The parties shall make all reasonable efforts to resolve their dispute by amicable negotiations and agree to provide, without prejudice, frank, candid, and timely disclosure of relevant facts, information and documents to facilitate these negotiations. |
|  | 8.3.3 | No later than 10 Working Days following receipt of a responding party’s Notice in Writing of reply under paragraph 8.3.1, the parties shall meet to attempt to reach agreement on any unresolved dispute. |
|  | 8.3.4 | If the dispute has not been resolved within 10 Working Days after receipt of a responding party’s Notice in Writing of reply under paragraph 8.3.1 or within such further period agreed by the parties, then subject to the Owner’s consent to arbitration in its sole discretion, either party may by the giving of Notice in Writing to the other party, refer the dispute to be finally resolved by arbitration under the latest edition of the CCDC-40 Rules for Mediation and Arbitration of Construction Disputes, as may be amended by agreement between the parties. Such arbitration shall be conducted in the jurisdiction of the Place of the Work.” |
|  | GC 8.4.2 | Delete paragraph 8.4.2 in its entirety and substitute the following: |
|  | “8.4.2 | Nothing in Part 8 of the General Conditions – DISPUTE RESOLUTION shall be construed in any way to limit a party from asserting any statutory right to a lien under applicable lien legislation of the jurisdiction of the Place of the Work and the assertion of such right by initiating judicial proceedings is not to be construed as a waiver of any right that the parties have under paragraph 8.3.4 of GC 8.3 – NEGOTIATION, MEDIATION AND ARBITRATION to agree to refer the dispute to arbitration to adjudicate the merits of the claim upon which such a lien is based.” |
|  | GC 9.1 | Delete paragraph 9.1.2 in its entirety and substitute the following paragraph: |
|  | “9.1.2 | Before commencing any Work, the Contractor shall determine the location of all underground utilities and structures indicated in the Contract Documents, or that are discoverable by applying to an inspection of the Place of the Work the standard of skill and care described in GC 3.14 – CONTRACTOR STANDARD OF CARE.” |
|  | GC 9.1 | Insert the following as a new paragraph after paragraph 9.1.4: |
|  | “9.1.5 | The Contractor shall be responsible for keeping the Place of the Work free from trespassers and for protection of the Work and the public from any loss or injury from commencement to completion and acceptance of the Work by the Owner. The Contractor shall provide all required barriers, fences, warning signs, lights and watching for the protection of persons and property on and adjacent to the Place of the Work.” |
|  | GC 9.2 | Delete GC 9.2 – TOXIC AND HAZARDOUS SUBSTANCES in its entirety and substitute the following: |
|  | “GC 9.2 | HAZARDOUS SUBSTANCES |
|  | 9.2.1 | The Owner shall be responsible for Hazardous Substances and materials present at the Place of the Work at the commencement of the Work. The Contractor shall be responsible Hazardous Substances brought onto the Place of the Work after commencement of the Work. |
|  | 9.2.2 | If the Contractor: .1 encounters Hazardous Substances at the Place of the Work, or .2 has reasonable grounds to believe that Hazardous Substances are present at the Place of the Work, in each case, which were not identified in the Contract Documents then the Contractor shall: .1 take all reasonable steps, including stopping the Work if necessary, to ensure that no individual’s exposure to any Hazardous Substances exceeds the exposure permitted by Environment Law; .2 to ensure all Environmental Laws are complied with; and .3 immediately report the circumstances in writing to the Consultant and the Owner in writing. |
|  | 9.2.3 | The Owner, in consultation with the Contractor, will retain a Qualified Environmental Professional to investigate and provide an opinion on: .1 the necessary steps required by Environmental Law to remove and dispose of any Hazardous Substances at the Place of the Work that must be moved in order to proceed with the Work; and .2 whether such Hazardous Substances were present prior at the Place of the Work prior to the commencement of the Work, or whether they were brought to the Place of the Work by the Contractor. |
|  | 9.2.4 | If the Owner and Contractor agree, or if the Qualified Environmental Professional referred to in paragraph 9.2.3 determines, that the Hazardous Substances were not brought onto the Place of the Work by the Contractor or anyone for whom the Contractor is responsible: .1 the Owner may engage the services of a Qualified Environmental Professional to arrange for the expeditious removal from the Place of the Work and disposal of the Hazardous Substances materials, the cost of which shall be to the account of the Owner, or the Owner may request that the Contractor shall within 10 Working Days prepare and deliver to the Owner, with a copy to the Consultant, a plan for the safe removal from the Place of the Work and disposal of the Hazardous Substances and the Owner shall, within 5 Working Days of receipt of such plan, approve the plan or provide reasons to the Contractor why the Owner did not approve the plan; .2 if having received approval from the Owner, the Contractor shall promptly take all necessary steps, in accordance with Environmental Law in force at the Place of the Work, to safely remove and dispose of the Hazardous Substances in accordance with the approved plan; .3 the Contractor shall make good any damage to the Work, the Owner’s property or property adjacent to the Place of the Work as provided in GC 9.1.3 of GC 9.1 — PROTECTION OF WORK AND PROPERTY; .4 the Owner shall reimburse the Contractor for the costs of all steps taken pursuant to GC 9.2.2 and 9.2.4, except in all cases where the Owner has retained and directly paid for the services of a Qualified Environmental Professional; .5 the Owner shall extend the Contract Time for such reasonable time as the Consultant may recommend in consultation with the Contractor and the Qualified Environmental Professional referred to in GC 9.2.3 and reimburse the Contractor for reasonable costs incurred as a result of the delay; and .6 the Owner shall indemnify the Contractor as required by GC 13.1 — INDEMNIFICATION. |
|  | 9.2.5 | If the Owner and Contractor agree, or if the Qualified Environmental Professional referred to in paragraph 9.2.3 determines, that the Hazardous Substances were brought onto the Place of the Work by the Contractor or anyone for whom the Contractor is responsible, then the Contractor shall: .1 within 10 Working Days prepare and deliver to the Owner, with a copy to the Consultant, a plan for the safe removal from the Place of the Work and disposal of the Hazardous Substances and the Owner shall, within 5 Working Days of receipt of such plan, approve the plan or provide reasons to the Contractor why the Owner did not approve the plan; .2 having received approval from the Owner, promptly take all necessary steps, in accordance with Environmental Law, to safely remove and dispose of the Hazardous Substances in accordance with the approved plan; .3 make good any damage to the Work, the Owner’s property or property adjacent to the Place of the Work as provided in paragraph 9.1.3 of GC 9.1 — PROTECTION OF WORK AND PROPERTY; .4 reimburse the Owner for reasonable expenses costs incurred with regard to the Qualified Environmental Professional under paragraph 9.2.3; and .5 indemnify the Owner as required by GC 13.1 — INDEMNIFICATION.” |
|  | GC 9.3.2 | In paragraph 9.3.2, insert the following after the words “Contractor shall” in the first line: “comply with the provisions of the Heritage Conservation Act (British Columbia) and”. |
|  | GC 9.4.1 | Delete GC 9.4 – CONSTRUCTION SAFETY in its entirety and substitute the following: |
|  | “GC 9.4 | CONSTRUCTION SAFETY |
|  | 9.4.1 | The Contractor shall be solely responsible for construction safety at the Place of the Work and for compliance with the rules, regulations and practices required by the applicable construction health and safety legislation and shall be responsible for initiating, maintaining and supervising all safety precautions and programs in connection with the performance of the Work. The Contractor shall assume overall responsibility, carry out and discharge all duties and obligations of, and be designated or registered as the “prime contractor” or equivalent role with respect to the health and construction safety legislation applicable to the Place of the Work and the Project. The Contractor shall be responsible for and ensure the safety not only of the workers, Subcontractors, tradesmen and Suppliers and their plant and equipment but also of all other persons who enter the Place of the Work (including the Owner and the Other Contractors and own forces) whether during working hours or not and for that purpose shall erect such hoardings and signs and shall employ such safety measures as may be necessary to ensure the safety of such persons. In order to effectively exercise that responsibility, the Owner authorizes the Contractor to supervise the Owner's own forces at the Place of the Work with respect to applicable health and construction safety matters and, where reasonably necessary due to health or construction safety considerations, deny the Owner's own forces or its Other Contractors access to the Place of the Work. |
|  | 9.4.2 | Either of the Owner or the Consultant shall have authority in an emergency to stop the progress of the Work whenever in its opinion such stoppage may be necessary to ensure the safety of life, or of the Work or neighbouring property. This includes authority to make changes in the Work, and to order, assess and award the cost of such work, extra to the Contract or otherwise, as may in its opinion be necessary. The Owner or the Consultant shall within two (2) Working Days confirm in writing any such instructions provided that where the Consultant has authorized changes to the Work, such confirmation in writing shall also be confirmed by the Owner. |
|  | 9.4.3 | Prior to commencement of the Work, and (where applicable) during the performance of the Work, the Contractor shall: .1 deliver to the Owner a current clearance certificate issued by the Workers’ Compensation Board of British Columbia (“WorkSafeBC”) and confirmation from WorkSafeBC of the Contractor’s current experience; .2 deliver to the Owner certificates of evidencing the Contractor’s insurance coverage that has application to the Project; .3 deliver to the Owner documentation of the Contractor’s in-house safety-related programs; .4 deliver to the Owner documentation of the Contractor’s Health and Safety plan specific to the Place of the Work; .5 procure that a copy of the Notice of Project is filed with WorkSafeBC naming itself as “prime contractor” under the occupational health and safety legislation applicable to the Place of the Work (“OHSA”), if required, or a copy of any provincially prescribed “Notice of Project” and all necessary permits, notifications and related health and safety documents; .6 ensure that each work space is properly delineated and protected by the necessary safety measures required by such legislation; .7 notify the Owner of any infraction or non-compliance with the Contractor’s health and safety directions, instructions, plans or policies by any of the Owner’s own forces or the Other Contractors and takes immediate action to ensure no further infractions or non-compliance; and .8 ensure that all Other Contractors, labour, Consultant, Subcontractors, Suppliers, personnel and site staff are fully familiar with the safety policy and procedure set down for the Project and shall aware that the Contractor is responsible for ensuring such procedure in accordance with the rules, regulations and law of the work place. |
|  | 9.4.4 | The Contractor hereby represents and warrants to the Owner that appropriate health and safety instruction and training have been provided and will be provided to the Contractor’s employees, Subcontractors and Suppliers, before the Work is commenced and agrees to provide the Owner, if requested, proof of such instruction and training. |
|  | 9.4.5 | The Contractor shall indemnify and save harmless the Owner, its board of governors, authorized representatives, agents, officers, directors, employees, consultants, successors and assigns from and against the consequences of any and all safety infractions committed by the Contractor under OHSA or applicable health and safety legislation in the Place of the Work, including the payment of legal fees and disbursements on a solicitor and client basis.” |
|  | GC 10.1.2 | Insert the following at the end of paragraph 10.1.2: |
|  |  | “For greater certainty, the Contractor shall not be entitled to any mark up for overhead or profit on any increase in such taxes and duties and the Owner shall not be entitled to any credit related to mark up for overhead or profit on any decrease in such taxes.” |
|  | GC 10.1.2 | Insert the following new paragraphs after paragraph 10.1.2: |
|  | “10.1.3 | Where an exemption or recovery of sales taxes, customs duties, excise taxes or Value Added Taxes is applicable to the Contract, the Contractor shall, at the request of the Owner or the Owner’s representative, assist, join in, or make application for any exemption, recovery, or refund of all such taxes and duties and all amounts recovered or exemptions obtained shall be for the sole benefit of the Owner. The Contractor agrees to endorse over to the Owner any funds received from the federal or provincial governments, or any other taxing authority, as may be required to give effect to this paragraph 10.1.3. |
|  | 10.1.4 | The Contractor shall maintain accurate records tabulating equipment, material and component costs reflecting the taxes, customs duties, excise taxes and Value Added Taxes paid. |
|  | 10.1.5 | Any refund of taxes, including without limitation, any government sales tax, customs duty, excise tax or Value Added Tax, whether or not paid, which is found to be inapplicable or for which exemption may be obtained, is the sole and exclusive property of the Owner. The Contractor agrees to cooperate with the Owner and obtain from all Subcontractors and Suppliers cooperation with the Owner in the application of any refund of any taxes, which cooperation shall include, but not limited to, making or concurring in the making of an application for any such refund or exemption and providing to the Owner copies, or where required, originals of records, invoices, purchase orders, and other documentation necessary to support such applications or exemptions or refunds. All such refunds shall either be paid to the Owner, or shall be a credit to the Owner against the Contract Price, in the Owner’s discretion. |
|  | 10.1.6 | Customs duties penalties, or any other penalty, fine or assessment levied against the Contractor shall not be treated as a tax or customs duty for purposes of this GC 10.1.” |
|  | GC 10.2.2 | Delete paragraphs 10.2.2 and 10.2.3 in their entirety and substitute the following: |
|  | “10.2.2 | The Owner shall obtain and pay for development approvals, building permits, permanent easements and rights of servitude necessary for the performance of the Work. |
|  | 10.2.3 | The Contractor shall be responsible for the procurement of all permits, licenses, inspections, and certificates, which are necessary for the performance of the Work other than those that are the responsibility of the Owner pursuant to paragraph 10.2.2. All necessary permits, licenses and certificates shall include the approval of Drawings and Specifications required by applicable provincial labour legislation. The Contract Price includes the cost of these permits, licenses, inspections, and certificates, and their procurement.” |
|  | GC 10.2.5 | Delete paragraphs 10.2.5 to 10.2.7 in their entirety and substitute the following: |
|  | “10.2.5 | The Contractor shall, to the extent only of the Contractor’s expertise, experience and knowledge, be responsible for verifying that the Contract Documents are in compliance with Applicable Laws, ordinances, rules, regulations, or codes relating to the Work. If the Contract Documents are at variance therewith, or if, subsequent to the time of bid closing, changes are made to Applicable Laws, ordinances, rules, regulations, or codes which require modification to the Contract Documents, the Contractor shall advise the Consultant in writing requesting direction immediately upon such variance or change becoming known, and no further Work on the affected components of the Contract shall proceed until these changes to the Contract Documents have been obtained by the Contractor from the Consultant. The Consultant will make the changes required to the Contract Documents as provided in GC 6.1 – OWNER’S RIGHT TO MAKE CHANGES, GC 6.2 – CHANGE ORDER and GC 6.3 – CHANGE DIRECTIVE. |
|  | 10.2.6 | If the Contractor fails to advise the Consultant in writing or fails to obtain direction as required in paragraph 10.2.5, and performs work that is contrary to any Applicable Laws, ordinances, rules, regulations or codes, then: .1 the Contractor shall be responsible for and shall correct the violations thereof and shall bear the costs, expenses and damages attributable to the failure to comply with the provisions of such Applicable Laws, ordinances, rules, regulations, or codes; and .2 if the Owner suffers loss or damage as a result of the Contractor’s failure to comply with paragraph 10.2.5, and notwithstanding any limitations described in paragraph 13.1.1, the Contractor agrees to indemnify and hold harmless the Owner and the Consultant from and against any claims, demands, losses, costs, damages, actions, suits or proceedings resulting from such failure by the Contractor. |
|  | 10.2.7 | The Contractor shall notify the Chief Building Official or the registered code agency where applicable, of the readiness, substantial completion, and completion of the stages of construction set out in the BC Building Code or authorities having jurisdiction as applicable. The Contractor shall be present at each site inspection made by an inspector or registered code agency as applicable under the BC Building Code, or authorities having jurisdiction as applicable. |
|  | 10.2.8 | The Contractor shall provide to the Consultant copies of all inspection reports from the various authorities having jurisdiction within two (2) Working Days of their receipt.” |
|  | GC 10.4 | Delete GC 10.4 – WORKERS’ COMPENSATION in its entirety and substitute the following: |
|  | “GC 10.4 | WORKERS’ COMPENSATION |
|  | 10.4.1 | Prior to commencing the Work, and with each application for payment thereafter, the Contractor shall provide a Certificate of Clearance from the Workers Compensation Board of BC/WorkSafe BC. Application for payment of the holdback amount following Substantial Performance of the Work and again at the Contractor’s application for final payment, the Contractor shall provide evidence of compliance by the Contractor, Subcontractors and Suppliers with the workers compensation legislation at the Place of the Work, including payments due thereunder. |
|  | 10.4.2 | At any time during the term of the Contract, when requested by the Owner, the Contractor shall provide such evidence of compliance by the Contractor, Subcontractors and Suppliers. |
|  | 10.4.3 | Occupational Health and Safety The Contractor shall act in the capacity of the “Prime Contractor” for the construction site and that it shall take all necessary precautions to fulfill all of its obligations, functions and duties as Prime Contractor in compliance with Workers Compensation Act (British Columbia) and the OHS Regulation. .1 The Contractor shall, before the commencement of the Work: (1) Designate a qualified site safety coordinator who shall be an employee of the Prime Contractor and shall be qualified (being knowledgeable of the work, the hazards involved and the means to control the hazards, by reason of education, training, experience or a combination thereof) to discharge the responsibilities of a site safety coordinator as described in the Workers Compensation Act (British Columbia) and the OHS Regulation; and (2) Deliver to the Owner’s representative written notice of the designation of the site safety coordinator a copy of the ‘Notice of Project’ for the Project. Written notice confirming that the Health and Safety Program has been implemented and is readily available in accordance with the Workers Compensation Act (British Columbia) and the OHS Regulation. .2 The Contractor shall: (1) Observe and comply with Workers Compensation Act (British Columbia) and the OHS Regulation, including conducting worker safety orientations, holding health and safety meetings to coordinate activities, conduct safety inspections to ensure compliance with WorkSafeBC OSH Regulations by all workers and perform accident and incident investigations as required; (2) Ensure that all assessment, levies, penalties, fees and fines, which may be made under any Health and Safety Laws, are punctually paid as they become due; and (3) Establish and maintain a joint health and safety committee with terms of reference that ensure that it can fulfill its functions under the Workers Compensation Act (British Columbia) and the OHS Regulation, and ensure that such committee fulfills such functions. .3 Post at the Place of the Work: (1) The name of the qualified coordinator; (2) A site drawing showing the boundaries of the construction site, with project layout, first aid location, emergency transportation provisions and the evacuation marshalling points relating to the Place of the Work; (3) Ensure that a copy of the Health and Safety Program, the written construction procedures designed to protect the health and safety of workers at the construction site and a copy of the OHS Regulation are readily available at convenient locations at the Place of the Work; (4) Deliver and post at the Place of the Work any and all required Notices of Project; (5) When conditions or activities at any location at the Place of the Work affect the workers of more than one employer or where there are overlapping or adjoining work activities by two or more employers, ensure that the site safety coordinator coordinates the occupational health and safety activities throughout the Place of the Work and alerts all workers to all reasonably foreseeable hazards to which they are likely to be exposed; (6) Immediately notify all employers, workers, Suppliers and Subcontractors and any other persons throughout the site of any hazard created by the construction work and/or by overlapping or adjoining work activities of two or more employers and ensure the hazards are addressed throughout the duration of such activities; (7) Immediately deliver to the Owner’s representative the name of any employer who does not cooperate with, assist or comply with the requirements of the site safety coordinator regarding coordination of health and safety activities throughout the Place of the Work; (8) In the event of an accident or incident that requires notification to WorkSafeBC, deliver copy of such notice to the Owner’s representative at the same time as to WorkSafeBC, and provide ongoing information to the Owner’s representative on the progress of any investigation resulting from such notice, accident or incident; (9) Record and retain all occupational health and safety documentation in respect of the Work, including: (i) Notices which the Contractor is required to provide to WorkSafeBC; (ii) Monthly summaries of remedial actions taken to reduce occupational health and safety hazards within the construction site; (iii) Directives with inspection reports issued by or through WorkSafeBC in connection with the construction site or the construction work; (iv) Reports and investigations on incidents and accidents, which are required to be investigated by WorkSafeBC; (v) Records, including minutes, of safety meetings and tailgate meetings; (vi) Copies of any hazard identifications performed at the Place of the Work; (vii) Evidence that instruction and health and safety orientation and training for workers at the Place of the Work is being conducted, and upon the request of the Owner’s representative, make such documentation available to the Owner’s representative, including by providing copies; and (10) Employ a qualified site safety coordinator at the construction site. |
|  | 10.4.4 | Site Safety and Security .1 The Contractor shall take such measures as are reasonably required, including fencing, hoarding, the use of delineators and signage where appropriate, to prevent the trespass and access into the Place of the Work of any persons not entitled to be on the site. .2 The Contractor shall provide for the safety of all persons at or near the Place of the Work including users of the site and shall maintain the Place of the Work in a manner and in an orderly state that ensures the safety of such persons and that is appropriate to the safety of such persons. .3 The Contractor shall remove from the Place of the Work any worker who engages in misconduct or is incompetent or negligent in the proper performance of any duties, or whose presence at the Place of the Work is otherwise undesirable. |
|  | 10.4.5 | Health and Safety Program .1 Notwithstanding any limitation in the WorkSafeBC OHS Regulation regarding the number of workers in any work force, the Contractor shall prepare, submit to the Owner’s representative, and at all times implement and a written health and safety program that: (1) is specific to controlling the hazards of the Project site; (2) complies with the WorkSafeBC OHS Regulation; (3) satisfies the requirements of Section 3.3 of Part 3 of the OHS Regulation; (4) is designed to prevent injuries and occupational diseases; (5) provides for the establishment and maintenance of systems and processes to ensure compliance with the WorkSafeBC OHS Regulation; and upon the request of the Owner’s representative from time to time, deliver to the Owner’s representative evidence of the implementation and maintenance of the Health and Safety Program. |
|  | 10.4.6 | Appointment of other Prime Contractors by the Owner .1 The Owner may, from time to time during the term of Contract, on prior written notice from the Owner’s representative to the Contractor, appoint a person other than the Contractor as the Prime Contractor in connection with specified works and activities that may be undertaken and performed at any specified location or locations in the Project site, for the specified period of time, all as set out in such notice. (1) Upon receipt of written notice from the Owner’s representative, the Contractor agrees that it will not be the Prime Contractor for the specified location or locations and for the specified period of time. (2) Upon receipt from the Owner’s representative of written notice of the conclusion of the works and activities, the Contractor shall reassume and thereafter fulfill the responsibilities of the Prime Contractor as otherwise set out in this Contract at the applicable location or locations. |
|  | 10.4.7 | The Contractor shall indemnify and hold harmless the Owner from and against all claims, demands, actions, suits or proceedings by any of the employees of the Contractor or Subcontractors in relation to occupational health and safety on the Project.” |
|  | GC 11.1 | Delete GC 11.1 – INSURANCE in its entirety and substitute with the following: |
|  | “GC 11.1 | INSURANCE |
|  | 11.1.1 | Without restricting the generality of GC 13.1 – INDEMNIFICATION, insurance and coverage will be arranged and paid for as under-noted: Insurance has been bought by the Owner, to protect all those who have a direct participation in the construction project for claims which may arise as a result of third party liability and loss or damage during course of construction. As coverage is designed to protect the various parties insured on the same basis as if each had bought separate policies, it is essential that each insured advise their insurance agent or broker to ensure that duplicate coverage does not occur. In general, the Contractor, all Subcontractors, Suppliers, architects, engineers, the Consultant and anyone employed by them to perform part or parts of the Work (but excluding Suppliers whose only function is to supply and/or transport Products to the Project site) shall exclude in their tender prices, insurance charges applicable to their Project work, as the premium is paid by the Owner. The value of such work shall be excluded in annual sales or audit reports given to underwriters for the purposes of fixing premiums, otherwise duplicate charges may result. The exception shall be long term “completed operations” coverage after the project is completed, and the liability insurance provided by the Owner has expired. (a) Commercial General Liability .1 The Owner shall provide, maintain, and pay for Commercial General Liability Insurance with a limit of TEN MILLION DOLLARS ($10,000,000) inclusive per occurrence, TWENTY MILLION DOLLARS ($20,000,000) general aggregate for bodily injury, death, and damage to property, including loss of use thereof. Products and completed operations liability with a limit of TEN MILLION DOLLARS ($10,000,000) Annual Aggregate. Such coverage excluding Marine & Aircraft Liability, Pollution Liability, and Professional Liability Insurance. .2 The insurance shall cover the Owner, Contractor, Subcontractors, architects, engineers, Consultants and anyone employed by them to perform part or parts of the Work but excluding Suppliers whose only function is to supply and/or transport Products to the Project site. The insurance does not extend to any activities, works, jobs or undertakings of the insureds other than those directly related to the Work under this Contract. .3 The insurance shall preclude subrogation claims by the insurer against anyone insured hereunder. .4 The insurance shall include coverage for: (1) Premises and Operations Liability; (2) Products and Completed Operations Liability (24 months); (3) Blanket Contractual Liability; (4) Cross Liability; (5) Elevator and Hoist Liability; (6) Contingent Employer’s Liability; (7) Personal Injury Liability; (8) Shoring, Blasting, Excavating, Underpinning, Demolition, Piledriving and Caisson Work, Work below Ground Surface, Tunnelling and Grading (as applicable); (9) Broad Form Property Damage; (10) Employees as Additional Insureds; .5 Any applicable deductible shall not exceed _______________ [NTD: Insert amount] ($__________) Except with respect to loss or damage arising from hot roofing operations, where the deductible shall not exceed _______________ [NTD: Insert amount]. .6 This insurance shall be maintained continuously from the commencement of the Work and kept in force until the Project has reached Substantial Completion or Ready-for-Takeover of the Work, whichever is earliest, plus with respect to completion operations coverage a further period of twenty-four (24) months. (b) Property Coverage .1 The Owner shall provide, maintain and pay for Course of Construction Coverage against “All Risks” of physical loss or damage, and cover all materials, property, structures, and equipment purchased for entering into or forming part of the work whilst located anywhere within Canada and continental United States of America (excluding Alaska) during construction, erection, installation, and testing, but such coverage shall not include coverage for faulty workmanship, materials or error in design or Contractor’s equipment of any description. Such transit and temporary location coverage shall have a limit of ONE HUNDRED THOUSAND DOLLARS ($100,000). .2 The insurance shall cover the Owner, Contractor, Subcontractors, architects, engineers, Consultants and anyone employed by them to perform part or parts of the Work but excluding Suppliers whose only function is to supply and/or transport Products to the Project site. .3 There will be a maximum deductible of _______________ [NTD: Insert amount] ($__________) for each and every occurrence on projects valued at less than TEN MILLION DOLLARS ($10,000,000) and a maximum deductible of _______________ [NTD: Insert amount] ($__________) on projects valued at more than TEN MILLION DOLLARS ($10,000,000) except for the perils of flood which shall have a maximum deductible of _______________ [NTD: Insert amount] ($__________), testing and commissioning and water damage to interior buildings shall have a maximum deductible of _______________ [NTD: Insert amount] ($__________) and earthquake shall have a twenty percent (20%) maximum deductible based upon the total project value insured subject to a minimum of TWO HUNDRED FIFTY THOUSAND DOLLARS ($250,000). .4 The coverage will contain a waiver of the Owner’s rights of subrogation claim against all protected entities except where a loss is deemed to have been caused by or resulting from any error in design of any other professional error or omission. .5 The Contractor shall, at its own expense, take all reasonable precautions to prevent fires occurring in or about the Work and shall observe, and comply with all insurance policy warranties and all laws and regulations in force respecting fires. .6 This insurance shall be maintained continuously from the commencement of the Work until Ready-for-Takeover. .7 Any failure of any insurer to pay any claim will in no way absolve the Contractor from its responsibilities and liabilities under the Contract. The agreement of the Owner to maintain insurance under the Contract is not deemed to extend or affect the obligation or liability of the Owner to the Contractor. (c) Automobile Liability Insurance The Contractor shall provide, maintain, and pay for, and require all Subcontractors, and Suppliers to provide, maintain, and pay for Automobile Liability Insurance in respect of all owned or leased vehicles, subject to limits of not less than FIVE MILLION DOLLARS ($5,000,000) inclusive per occurrence. The insurance shall be placed with such company or companies as in such form and with such deductibles as may be acceptable to the Owner. (d) Products and Completed Operations Liability Insurance The Contractor shall provide, maintain, and pay for, products and completed operations liability insurance with a limit of TEN MILLION DOLLARS ($10,000,000) Annual Aggregate. Any insurance required under this clause 11.1.1(d) must name the Owner as an additional insured, but only with respect to liability arising out of the Contractor’s or the Subcontractor’s performance of the work. This insurance shall be maintained continuously from the date that the Owner’s completion operations coverage expires pursuant to clause 11.1.1(a).6 for a period of forty-eight (48) months. (e) Pollution Liability Insurance Where the Contractor’s performance or the Subcontractor’s performance of the Work is associated with hazardous materials clean up, removal and/or containment, transit, or disposal. This insurance must have a limit of liability not less than TWO MILLION DOLLARS ($2,000,000) inclusive per occurrence insuring against bodily injury, death, and damage to property including loss of use thereof. Any insurance required under this clause 11.1.1(e) must name the Owner as an additional insured, but only with respect to liability arising out of the Contractor’s or the Subcontractor’s performance of the work. Such insurance must include sudden and accidental, and gradual pollution events for third party liability including ongoing and completed operations and shall not be impaired by any, biological contaminants (without limitation, mould and bacteria), asbestos, or lead exclusions. Any 'insured vs. insured' exclusion shall not prejudice coverage for the Owner and shall not affect the Owner's ability to bring suit against the Contractor as a third party. This insurance shall be maintained continuously from commencement of the work involving hazardous materials clean-up, removal and/or containment, transit and disposal until such work is completed and including a twenty-four (24) month extended reporting period if any such insurance is provided on a claims-made basis. |
|  | 11.1.2 | The description of the Owner arranged insurance described herein is provided on a summary basis only and is not a statement of the actual policy terms and conditions. The Owner does not represent or warrant that the Owner arranged insurance contains insurance for any and all losses. It is the Contractor’s responsibility to ascertain the exact nature and extent of coverage provided by the Owner arranged insurance, to review all policies pertaining thereto and to obtain any other insurance that it may be prudent for the Contractor to obtain. |
|  | 11.1.3 | The Contractor will ensure that all activities, procedures and conduct at the Place of the Work, on the Owner’s property or in connection with the Work comply with the requirements of all insurance policies applicable to the Work or the Project and all directives, instructions and riders issued by the insurers pursuant to or in conjunction with such policies. The Contractor will ensure that its activities and the activities of those for whom it is responsible (including each Subcontractor and Supplier) comply with all insurance requirements so that in the event of any claim, insurance coverage is not minimized or denied wholly or in part due to any such activities. |
|  | 11.1.4 | At the time of any occurrence covered, or any occurrence appearing to be covered, by any of the policies of insurance, the Contractor shall immediately give notice to the occurrence, in writing, to the representative of the Owner. |
|  | 11.1.5 | The parties shall pay their share of the deductible amounts in direct proportion to their responsibility in regards to any loss for which the above policies are required to pay, except where such amounts may be excluded by the terms of the contract. |
|  | 11.1.6 | The Contractor shall provide, maintain and pay for any additional insurance which the Contractor is required to provide by law, which the Owner requires, or which the Contractor considers necessary to cover risks not otherwise covered by insurance specified in paragraph 11.1.1. All such insurances provided and maintained by the Contractor will name the Owner an additional insured and will include (but not be limited to) aircraft and/or watercraft liability, and special transit risks. |
|  | 11.1.7 | The Owner will not be responsible for injury to the Contractor’s employees or for loss or damage to the Contractor’s “Construction Equipment”, or to the Contractor’s employees’ machinery, equipment, tools or supplies which may be temporarily used or stored in, on or about the project site during construction and which may, from time to time, or at the termination of this Contract, be removed from the project site. The Contractor hereby waives all rights of recourse against the Owner with regard to damage to the Contractor’s property. For greater certainty, this paragraph 11.1.7 shall in no way affect the indemnity obligations of the Owner and Contractor under GC 13.1 – INDEMNIFICATION. |
|  | 11.1.8 | If the Contractor or any of the Subcontractors fail to obtain or maintain insurance as required hereunder or if the Owner does not approve any insurance policy or policies submitted and the Contractor thereafter does not meet the requirements of the Owner as to terms and conditions of the insurance, the Owner shall have the right to place and maintain such insurance in the name of the Contractor and the Owner. The cost thereof shall be payable by the Contractor to the Owner on demand and the Owner may deduct the cost thereof from any monies which are due or may become due to the Contractor. If coverage shall lapse, all work by the Contractor and Subcontractors shall cease until satisfactory evidence of renewal is produced. |
|  | 11.1.9 | Each insurance policy provided by the Contractor, Subcontractor, or any Supplier shall be endorsed as follows: “Notice: It is hereby understood and agreed that this policy will not be cancelled, reduced, materially altered or amended without the insurer giving at least thirty (30) days’ prior written notice by registered mail to: Facilities Management UNIVERSITY OF VICTORIA Saunders Building 3800 Finnerty Road, Victoria, B.C. V8W 2Y2. |
|  | 11.1.10 | Upon request, the Contractor and Subcontractors shall provide their insurance loss history for the previous five (5) years within ten (10) Working Days, or if the Contractor or Subcontractors have less than five (5) years of insurance loss history, all of their insurance loss history, which shall in either case include the following coverages: .1 Builder’s Risk or Course of Construction, .2 Commercial General Liability, and .3 Wrap Up Liability.” |
|  | GC 11.2 | Insert the following new GC 11.2 – CONTRACT SECURITY following GC 11.1: |
|  | “GC 11.2 | CONTRACT SECURITY |
|  | 11.2.1 | The Contractor shall, prior to the commencement of the Work (or, if earlier, within the time specified in the procurement documents applicable to the Project), furnish to the Owner the following: .1 a performance bond, in an amount equal to at least fifty percent (50%) of the Contract Price; and .2 a labour and material payment bond, in an amount equal to at least fifty percent (50%) of the Contract Price, in each case, in a form and amount approved by the Owner. |
|  | 11.2.2 | Such bonds shall be issued by a duly licensed surety company authorized to transact the business of suretyship in the province or territory of the Place of the Work and shall be maintained in good standing until the fulfillment of the Contract. The form of such bonds shall be in accordance with the latest edition of the CCDC approved bond forms. Each such bond must be in a form approved by the Insurance Bureau of Canada. |
|  | 11.2.3 | The Contractor shall give the Owner Notice in Writing of any material change in any surety within 15 days of the occurrence of such change.” |
|  | 12.1.1 | Replace the words “as-built drawings completed to date on site” with the words “As-Built Drawings” in paragraph 12.1.1.5. Insert the following new paragraph following paragraph 12.1.1.8: |
|  | “12.1.1.9 | The delivery to the Owner of an inventory record of the amount and location of machinery and equipment incorporated in the Work.” |
|  | 12.1.2 | Delete paragraph 12.1.2 in its entirety and substitute the following: |
|  | “12.1.2 | If the Contractor could not have, with all requisite diligence and attention, practicably obtained one or more of the items listed in paragraphs 12.1.1.3 to 12.1.1.6 for the time of Ready-for-Takeover, then delivery of such items may be deferred until the date that is 30 days following Ready-for-Takeover.” |
|  | 12.1.4 | Delete sub-paragraphs 12.1.4.1 and 12.1.4.2 in their entirety and substitute the following new sub-paragraphs after paragraph 12.1.4: |
|  |  | “.1 advise the Contractor in writing that the Work or the designated portion of the Work is not Ready-for-Takeover and give reasons why, or .2 confirm to the Owner and the Contractor in writing that the Work or a designated portion of the Work is Ready-for-Takeover, and the date of such confirmation shall be the Ready-for-Takeover date.” |
|  | 12.1.5 | In paragraph 12.1.5, insert the phrase “and correcting any deficient Work, as applicable” after the phrase “date for finishing the Work”. |
|  | 12.2. | Delete GC 12.2 – EARLY OCCUPANCY BY THE OWNER in its entirety and substitute the following: |
|  | “12.2 | EARLY OCCUPANCY BY THE OWNER |
|  | 12.2.1 | The Owner reserves the right to take occupancy of a part or the entirety of the Work before Ready-for-Takeover has been attained, in addition to occupancy conditions included in the Contract provided that: .1 the portion of the Work is ready to be used for the purpose intended, to the satisfaction of the Consultant and authorities having jurisdiction; and .2 the Owner’s possession and use do not interfere with the Contractor’s Work; and .3 the Consultant conducts a review prior to possession by the Owner; and .4 any extra costs incurred by the Contractor as a result of such occupancy are borne by the Owner, subject to the provisions of GC 6.5 - DELAYS. This shall not relieve the Contractor’s responsibility to complete the Work in a timely manner.” |
|  | GC 12.3.1 | Delete paragraph 12.3.1 in its entirety and substitute the following: |
|  | “12.3.1 | Except as otherwise provided herein, the warranty period under this Contract is the longer of: .1 one (1) year from the date Ready-for-Takeover has been attained; .2 such longer periods specified in the Contract Documents for certain portions of the Work or Products, and .3 in the case of Work done pursuant to a Subcontract, the longer warranty period, if any, provided for in such Subcontract.” |
|  | GC 12.3.3 | Delete paragraph 12.3.3 in its entirety and substitute the following: |
|  | “12.3.3 | The Owner, through the Consultant, shall promptly give the Contractor Notice in Writing of observed defects and deficiencies that occur during the relevant warranty period.” |
|  | 12.3.4 | Delete paragraph 12.3.4 in its entirety and substitute the following: |
|  | “12.3.4 | Subject to paragraph 12.3.2, the Contractor shall correct promptly, at the Contractor’s expense, defects or deficiencies in the Work which appear prior to and during the relevant warranty period. In effecting a correction of defects or deficiencies, the Contractor shall also bear all costs involved in removing, replacing, repairing, or restoring aspects of the Work that may be affected in the process of making the correction.” |
|  | 12.3.6 | Insert the following new paragraphs after paragraph 12.3.6: |
|  | “12.3.7 | The Contractor shall be responsible for obtaining Product warranties in excess of one (1) year on behalf of the Owner from the manufacturer. These Product warranties shall be issued by the manufacturer to the benefit of the Owner. The warranty shall include the prompt remedy of defects and/or failures in the equipment, material and installation upon written notification from the Owner. The warranty shall include further making good other work, components and finishes and other property damaged or disturbed in the course of remedying defects at no cost to Owner. The Contractor shall be responsible for obtaining warranties in excess of one (1) year on behalf of the Owner from each Subcontractor where the Owner has specified such longer warranty period. |
|  | 12.3.8 | Notwithstanding the provisions of this Article, if any statute in force in British Columbia creates a more extended liability for faulty materials or workmanship, then the provisions of such statute shall apply. Warranties shall not be deemed to restrict any liability of the Contractor arising out of any Applicable Laws. |
|  | 12.3.9 | The Contractor itself is contractually responsible to the Owner for, and will enforce, the warranty obligations of the Subcontractors and those of its manufacturers and Suppliers and ensure that Subcontractors correct promptly, at their own expense, defects or deficiencies which appear in their work during the period of one (1) year from the Ready-for-Takeover date (or such longer period as may be specified in a Subcontract or supply contract). Costs incurred by the Contractor with respect to administering this warranty and any miscellaneous costs incurred on site during the warranty period will be at the Contractor’s expense and shall not increase the Contract Price.” |
|  | GC 13.1.1 | Delete paragraph 13.1.1 in its entirety and substitute the following: |
|  | “13.1.1 | Without restricting the parties’ obligation to indemnify as described in paragraphs 13.1.4 and 13.1.5 the Owner and the Contractor shall each indemnify and hold harmless the other and their representatives, directors, governors, officers and employees and, in the case of the Owner, its board of governors, in each case, from and against all claims, demands, losses, costs (including without limitation reasonable legal fees), damages, actions, suits, or proceedings whether in respect to losses suffered by them or in respect to claims by third parties that arise out of, or are attributable in any respect to their involvement as parties to this contract, to the extent that such claims are: .1 caused or contributed to by: (1) the wilful act or negligence of the party from whom indemnification is sought or anyone for whose wilful acts or negligence that party is responsible at law, or (2) a failure of the party from whom indemnification is sought to fulfill its obligations under this Contract; and .2 made by Notice in Writing within such periods as prescribed by the Limitation Act (British Columbia).” |
|  | GC 13.1.2 | Delete paragraph 13.1.2 in its entirety and insert “Intentionally blank”. |
|  | GC 13.1.4 | In line 3 of paragraph 13.1.4, delete the words, “TOXIC AND”. |
|  | GC 13.1.6 | Insert the following new paragraph following paragraph 13.1.6: |
|  | “13.1.7 | Unless expressly stated otherwise in the Contract, in no circumstances will the Owner be liable to the Contractor under or connection with the Contract, whether arising in contract, tort, strict liability, indemnity or otherwise, for any Indirect Loss.” |
|  | GC 13.2.1 | Delete paragraph 13.2.1 in its entirety and substitute the following: |
|  | “13.2.1 | The Contractor’s request or application for confirmation that Ready-for-Takeover has been attained shall constitute a waiver and release by the Contractor of any and all claims which the Contractor has or reasonably ought to have knowledge of that could be advanced by the Contractor against the Owner arising from the Contractor’s involvement in the Work, including, without limitation, those arising from negligence or breach of contract in respect to which the cause of action is based upon acts or omissions which occurred prior to or on the Ready-for-Takeover date, except as follows: .1 claims arising prior to or on the Ready-for-Takeover date for which Notice in Writing of claim has been received by the Owner from the Contractor together with or prior to the Contractor’s request or application for confirmation that Ready-for-Takeover has been attained; .2 indemnification for claims advanced against the Contractor by third parties for which a right of indemnification may be asserted by the Contractor against the Owner pursuant to the provisions of this Contract; .3 claims for which a right of indemnity could be asserted by the Contractor pursuant to the provisions of paragraphs 13.1.4 or 13.1.5 of GC 13.1 – INDEMNIFICATION; and .4 claims resulting from acts or omissions which occur after the Ready-for-Takeover date.” |
|  | GC 13.2.3 | Delete paragraph 13.2.3 in its entirety and substitute the following: |
|  | “13.2.3 | Confirmation of Ready-for-Takeover shall constitute a waiver and release by the Owner of any and all claims which the Owner has or reasonably ought to have knowledge of that could be advanced by the Owner against the Contractor arising from the Owner’s involvement in the Work, including, without limitation, those arising from negligence or breach of contract in respect to which the cause of action is based upon acts or omissions which occurred prior to or on the Ready-for-Takeover date, except as follows: .1 claims arising prior to or on the Ready-for-Takeover date for which Notice in Writing of claim has been received by the Contractor from the Owner together with or prior to confirmation of Ready-for-Takeover; .2 indemnification for claims advanced against the Owner by third parties for which a right of indemnification may be asserted by the Owner against the Contractor pursuant to the provisions of this Contract; .3 claims arising from a breach of Applicable Law by the Contractor; .4 claims for which a right of indemnity could be asserted by the Owner against the Contractor pursuant to the provisions of GC 13.1 – INDEMNIFICATION, GC 9.2 – HAZARDOUS SUBSTANCES, GC 9.5 – MOULD, or any other provision of this Contract pursuant to which the Contractor has indemnified the Owner; .5 damages arising from the Contractor’s actions which result in substantial defects or deficiencies in the Work. “Substantial defects or deficiencies” mean those defects or deficiencies in the Work which affect the Work to such an extent or in such a manner that a significant part or the whole of the Work is unfit for the purpose intended by the Contract Documents or for which the aggregate cost of repair or remedying the defects or deficiencies would be greater than $500,000 or would be greater than 10% of the original Contract Price; .6 claims arising pursuant to GC 12.3 - WARRANTY; and .7 claims arising from acts or omissions which occur after the Ready-for-Takeover date.” |
|  | GC 13.2.4 | Delete paragraph 13.2.4 in its entirety and substitute the following: |
|  | “13.2.4 | The Owner waives and releases the Contractor from all claims referred to in paragraph 13.2.3.5 except claims for which Notice in Writing of claim has been received by the Contractor from the Owner within a period of six years from the Ready-for-Takeover date or, as to any defect or deficiency or other claim of which the Owner is not aware at the end of the said period of six years, a period of one year after the Owner has become aware.” |
|  | GC 13.2.9 | In paragraph 13.2.9, insert immediately before the words “further interim” and again immediately before the words “submit a final account”, the following: “, upon request,”. Insert the following at the end of paragraph 13.2.9: “For greater certainty, in paragraphs 13.2.1, 13.2.2, 13.2.3 and 13.2.5, “claims” includes claims based on changes and delay - e.g. under Part 6 of the General Conditions – CHANGES IN THE WORK.” |
|  | GC 14.1 | Insert the following new General Condition GC 14 – CONTRACTOR REPRESENTATIONS: |
|  | “PART 14 | CONTRACTOR REPRESENTATIONS |
|  | GC 14.1 | CONTRACTOR REPRESENTATIONS |
|  | 14.1.1 | The Contractor represents and warrants to the Owner as follows: .1 it has the corporate power and authority, and has obtained all necessary corporate approvals, to enter into and to perform all of its obligations under the Contract, and the Contract has been validly executed and delivered by the Contractor and constitutes a legal, valid and binding obligation of the Contractor enforceable in accordance with its terms; .2 subject to paragraph 6.4.1 of GC 6.4 – CONCEALED OR UNKNOWN CONDITIONS, it has or shall carefully examine all such information applicable to the Work and the Place of the Work, and is familiar with the physical condition of the Place of the Work and surrounding terrain and has or shall become fully informed as to all existing conditions and limitations; .3 it is qualified and has the necessary experience, skill, capacity and resources to perform the Work in accordance with the Contract within the Contract Time; .4 it is properly licensed, equipped, organized and financed to perform all its obligations under the Contract and that there are no agreements in existence that would affect Contractor’s ability to perform its obligations under the Contract in a timely and satisfactory manner; .5 the Work shall be performed in accordance with the terms of the Contract Documents and all Applicable Laws; and .6 the Work and any deliverables to be provided by the Contractor under the Contract will not contravene any copyright, patent, trade secret or other intellectual property right of any other Person and good title to such deliverables will pass to the Owner free and clear of any such claims, liens, charges or other encumbrances of any kind.” |
|  | GC 14 | Insert the following new General Condition GC 15 – FREEDOM OF INFORMATION AND PRIVACY: |
|  | “PART 15 | FREEDOM OF INFORMATION AND PRIVACY |
|  | GC 15.1 | FREEDOM OF INFORMATION AND PRIVACY |
|  | 15.1.1 | The Owner is subject to the Freedom of Information and Protection of Privacy Act R.S.B.C. 1996 c.165 (“FIPPA”). Disclosure or release of information may be required under this legislation. |
|  | 15.1.2 | The Owner may choose, in the interest of public accountability, or may be required by FIPPA, to make public or disclose this contract and associated records and information, in whole or in part. The Contractor agrees that the Owner shall be entitled to do so and consents thereto (except only for any specific information isolated and identified by the Contractor as confidential, and for which, where required by the Owner in response to an access request under FIPPA, the Contractor establishes that disclosure is excluded under FIPPA). |
|  | 15.1.3 | If the Contractor falls within the meaning of "service provider" as that term is defined under FIPPA, then the Contractor shall comply with applicable requirements of FIPPA relative to personal information.” |
|  | GC 16 | Insert the following new General Condition GC 16 – MISCELLANEOUS: |
|  | “PART 16 | MISCELLANEOUS |
|  | GC 16.1 | SEVERABILITY |
|  | 16.1.1 | Any provision of the Contract which is found to be illegal, invalid, void, prohibited or unenforceable shall be separate and severable from the remainder of the Contract and ineffective to the extent of such illegality, invalidity, avoidance, prohibition or unenforceability, without affecting any of the other provisions of the Contract, all of which shall remain in force and be binding upon the parties. |
|  | GC 16.2 | LABOUR |
|  | 16.2.1 | The Owner reserves the right to award separate contracts in connection with other parts of the Project to Other Contractors and to perform work with the Owner's own forces which other contractor or own forces or both are or may become unionized or non-unionized. |
|  | 16.2.2 | Any disruptions or delays caused by industrial relations disputes including jurisdictional disputes involving union, non-union workers or both on or related to the Place of the Work shall be the responsibility of the Contractor, and any costs arising out of any such disputes shall be deemed to be included in the Contract Price. |
|  | 16.2.3 | If the Contractor or any Subcontractor or Supplier is involved in a labour dispute including without limitation, strike, lockout, work stoppage, whether legal or illegal, which in any way materially detrimentally affects the Project, the Contractor agrees to defend, indemnify and save harmless the Owner and the Consultant from and against claims, demands, losses, costs, damages, actions, suits or proceedings whatsoever that arise out of or in connection with such labour dispute, and, notwithstanding any other provisions contained in the Contract Documents to the contrary, in such event the Contractor agrees that the Owner may terminate the Contractor's right to continue with the Work in whole or in part or terminate the Contract upon five (5) Working Days Notice in Writing to the Contractor and the provisions of paragraphs 7.1.5 and 7.1.6 of GC 7.1 shall apply. |
|  | GC 16.3 | CONFLICT OF INTEREST |
|  | 16.3.1 | The Contractor, all of the Subcontractors, and any of their respective advisors, partners, directors, officers, employees, agents, and volunteers shall not engage in any activity or provide any services where such activity or the provision of such services creates a conflict of interest (actually or potentially, in the sole opinion of the Owner) with the provision of the Work pursuant to the Contract. The Contractor acknowledges and agrees that a conflict of interest includes the use of Owner Confidential Information where the Owner has not specifically authorized such use. |
|  | 16.3.2 | The Contractor shall disclose to the Owner, in writing, without delay any actual or potential situation that may be reasonably interpreted as either a conflict of interest or a potential conflict of interest, including the retention of any Subcontractor or Supplier that is directly or indirectly affiliated with or related to the Contractor. |
|  | 16.3.3 | The Contractor covenants and agrees that it will not hire or retain the services of any employee or previous employee of the Owner where to do so constitutes a breach by such employee or previous employee of the employee or previous employee’s employment contract or the previous employer’s conflict of interest policy, as it may be amended from time to time. |
|  | 16.3.4 | A breach of this General Condition by the Contractor, any of the Subcontractors, or any of their respective advisors, partners, directors, officers, employees, agents, and volunteers shall entitle the Owner to terminate the Contract, in addition to any other rights and remedies that the Owner has in the Contract, in law, or in equity. |
|  | GC 16.4 | RELATIONSHIP BETWEEN THE PARTIES |
|  | 16.4.1 | The Contractor acknowledges and agrees that it is acting strictly as an independent contractor under Applicable Law, and not as an employee of the Owner. Nothing in this Contract will be deemed or construed to create a joint venture, partnership, or agency relationship between the parties for any purpose. Neither the Contractor, nor any employee, Subcontractor, Supplier or agent of the Contractor, shall hold themselves out as being or shall be construed to be employees or agents of the Owner. |
|  | GC 16.5 | AUDIT |
|  | 16.5.1 | For seven (7) years following the expiry or termination of this Contract, the Contractor shall maintain and retain complete and accurate records and documents pertaining to this Contract and the furnishing of the Work including all necessary records to substantiate all charges and payments under this Contract and that the Work was completed in accordance with the Contract and with Applicable Law. |
|  | 16.5.2 | During the term of this Contract and for seven (7) years after the term, the Contractor shall permit and assist the Owner in conducting audits of the operations of the Contractor to verify all charges and payments under this Contract and that the Work was completed in accordance with the Contract and with Applicable Law. The Owner shall provide the Contractor with at least ten (10) Working Days’ prior notice of its requirement for such an audit. If any such audit or inspection, (i) reveals the payments paid by the Owner to be incorrect, so that such error resulted in an overpayment by the Owner equal to or greater than the lesser of $25,000 or 2.5% of Contract Price required to be paid by the Owner in accordance with this Contract, or (ii) reveals any breach, violation or non-performance by the Contractor of any term, condition, representation, warranty or covenant contained in this Contract, then in each case, the Contractor shall (in addition to forthwith reimbursing the Owner for any overpayment) pay all costs incurred by the Owner with respect to any audit(s) and/or inspection(s) that uncovered such error, including the costs of any internal and external auditors, accountants and associates of the Owner directly involved with such process. |
|  | GC 16.6 | SCOPE OF WAIVER, RELEASE AND INDEMNITIES IN OWNER’S FAVOUR |
|  | 16.6.1 | In all provisions of the Contract containing a release or disclaimer or waiver or exculpatory language in favour of the Owner or an indemnity in favour of the Owner, references to the Owner include (whether or not expressly stated) the University of Victoria Board of Governors and each member thereof, and all directors, officers, agents and employees of the Owner, and the Consultant and the directors, officers, agents and employees of the Consultant, it being understood and agreed that, for this clause and all such provisions of the Contract, the Owner is deemed to be acting as agent and trustee on behalf of them and for their benefit to the extent necessary for them to receive and be entitled to the benefits of this clause and such provisions. The Contractor will, upon the request from time to time of the Owner, execute and deliver, under seal as a deed if so requested by the Owner, an affirmation and covenant in favour of any one or more of the said persons, as may be nominated from time to time by the Owner, in form and content reasonably prescribed by the Owner, to give effect or further effect, if deemed necessary by the Owner in its sole determination, to the provisions of this clause. |

END OF SUPPLEMENTARY CONDITIONS