| Step | Action | Resources | Who | Comments |
| --- | --- | --- | --- | --- |
| 1 | Consult with Head of academic unit | Discussion re: academic planning | New program lead | Head of academic unit to confirm new program as priority. |
| 2 | Consult with Disciplinary Dean | Discussion re: academic resource planning | Head of academic unit | Disciplinary Dean to confirm new program as priority. |
| 3 | Consult with the Associate Vice-President Academic Programs (AVPAP). | Discussion re: resources to support the proposed program. | Head of academic unit and disciplinary Dean | All new programs to be part of Faculty resource planning documentation. |
| 4 | Create Kuali entry with appropriate approval workflow. Senate Committee on Curriculum (SCC) approval required. | Kuali | Academic unit | Discuss documentation and submission to SCC. |
| 5 | Complete the Ministry Stage 1 template and the Supplemental New Undergraduate Degree template, obtain all required consultation documentation and approvals as indicated on the template. Submit the proposal to AVPAP along with an internal consultation form for each area of consultation. The proposal will then be posted to a secure MS Teams channel for internal consultation. Once complete, the proposal will be returned to the unit for revision. Internal consultations must be initiated at least eight (8 weeks before the submission deadline via the SCP Consultations MS Teams channel. - *A completed consultation form for each consultation must be submitted with the final proposal. If non-standard tuition and/or special fees are proposed, complete and submit tuition template to AVPAP separate from the proposal. | Approval steps for new undergraduate degree programs as per the VPAC website. Internal consultation template on VPAC website. Non-standard tuition template on VPAC site. | Academic unit | **Complete the Ministry Stage 1 template before completing the Supplemental New Undergraduate Degree template. Include letters of support for external consultations. All program proposals require units to complete the IACE consultation template and the internal consultation template. |
| 6 | - Resource requirements approval (signed by the Faculty Dean). *Please complete the New and Revised Academic Program Resource Requirement template and submit to the VPAC office a minimum of eight (8) weeks prior to submitting this proposal to the Senate Committee on Planning. | New and Revised Academic Program Resource Requirement template on VPAC website Academic unit | Academic unit | The New and Revised Academic Program Resource Requirement template should be submitted separately to the AVPAP only. This is not part of the proposal as resources are not considered by SCP; however resource requirements are considered by the Board of Governors. |
| 7 | Ministry and supplemental templates (proposal) submitted to Senate Committee on Planning (SCP). |  | Disciplinary Dean | Academic unit and Dean make a short presentation to SCP and respond to questions. |
| 8 | Proposal submitted for Senate approval by Admin to AVPAP. |  | AVPAP introduces the new program to Senate | Dean and Academic unit respond to questions about academic content. |
| 9 | Proposal submitted for Board of Governors approval by Admin to AVPAP. |  | VPAC introduces the new program to Board of Governors | Resource allocations must be approved by Board. |
| 10 | Submission to the Ministry of Post-Secondary Education and Future Skills for review/approval. |  | AVPAP’s Office | **Dean and the academic unit will be notified by AVPAP once Ministry approval is granted. |