| Step | Action | Resources | Who | Comments |
| --- | --- | --- | --- | --- |
| 1 | - Consult with Head of academic unit | Discussion re: academic resource planning | New program lead | Head of academic unit to confirm new program as priority. |
| 2 | - Consult the disciplinary Dean | Discussion re: academic resource planning | Head of academic unit | Head of academic unit to confirm new program as a priority. |
| 3 | - Consult Associate Vice-President Academic Planning (AVPAP) together with Faculty of Graduate Studies (FGS) Dean. | Discussion regarding resources to support the proposed program and tuition structure. | Head of Academic unit and disciplinary Dean | All new programs to be part of Faculty resource planning documentation. |
| 4 | - Consult FGS Administrative Manager to review process & timelines for GEC approval |  | Representative from the academic unit | Discuss FGS and curriculum approval process and requirements. |
| 5 | - Create Kuali entry with appropriate approval workflow. Senate Committee on Curriculum (SCC) approval required. | Kuali | Academic unit | Discuss documentation and submission to SCC. |
| 6 | - Complete the Ministry and FGS supplemental templates; obtain all required approvals as indicated on the template. Submit the proposal to AVPAP along with an internal consultation form for each area of consultation. The proposal will then be posted to a secure MS Teams channel for internal consultation. Once complete, the proposal will be returned to the unit for revision. - Internal consultations must be initiated at least eight (8) weeks before the GEC submission deadline via the SCP Consultations MS Teams channel. - *A completed consultation form for each consultation must be submitted with the final proposal. - If non-standard tuition and/or special fees are proposed, complete and submit tuition template to AVPAP separate from the proposal. | Approval steps for new degree –graduate, and template on VPAC website. Internal consultation template on VPAC website. Non-standard tuition template on VPAC site. | Academic unit | Include letters of support for external consultations. All program proposals require units to complete the IACE consultation template and the internal consultation template. |
| 7 | - Resource requirements approval (signed by the Faculty Dean) - *Please complete the New and Revised Academic Program Resource Requirement template and submit to the VPAC office a minimum of eight (8) weeks prior to submitting this proposal to the Senate Committee on Planning. | New and Revised Academic Program Resource Requirement template on VPAC website. | Academic unit | The New and Revised Academic Program Resource Requirement template should be submitted separately to the AVPAP only. This is not part of the proposal as resources are not considered by SCP; however resource requirements are considered by the Board of Governors. |
| 8 | - Completed template (proposal) submitted to FGS for Graduate Executive Committee approval |  | Academic unit | Academic unit makes a short presentation to GEC and responds to questions. Revisions made as required by GEC. |
| 9 | Proposal submitted to Senate Committee on Planning for approval / recommendation to Senate. |  | Dean of FGS submits to AVPAP after GEC | Faculty Dean or designate makes a short presentation to SCP and responds to questions. |
| 10 | Proposal submitted for Senate approval by Admin to AVPAP. |  | AVPAP introduces the proposal to Senate. | Dean and academic unit respond to questions about academic content. |
| 11 | Proposal submitted for Board of Governors approval by Admin to AVPAP. |  | VPAC introduces the proposal to Board of Governors. | Resource allocations must be approved by Board. |
| 12 | Submission to the Ministry of Post-Secondary Education and Future Skills for review/approval |  | AVPAP office | Deans and the academic unit will be notified by the AVPAP once Ministry approval is granted. |