| Step | Action | Resources | Who | Comments |
| --- | --- | --- | --- | --- |
| 1 | Consult with Head of academic unit | Discussion regarding academic planning | New program lead | Head of academic unit to confirm new program as priority. |
| 2 | Consult the Disciplinary Dean | Discussion regarding academic resource planning | Head of academic units | Dean to confirm new stream as a priority. |
| 3 | Consult the Associate Vice-President Academic Programs (AVPAP). **For graduate micro-certificate programs, consult with the AVPAP and the Dean of Graduate Studies. | Discussion regarding resources to support the proposed program, tuition template available on the VPAC website. | Head of academic unit and disciplinary Dean | All new streams should appear in Faculty resource planning documentation. |
| 4 | Complete standard template for new micro-certificate program; obtain all required approvals as indicated on the template. If non-standard tuition and/or special fees are proposed, submit non-standard tuition template to AVPAP. Submit the proposal to AVPAP along with an internal consultation form for each area of consultation. The proposal will then be posted to a secure MS Teams channel for internal consultation. Once complete, the proposal will be returned to the unit for revision. Internal consultations must be initiated at least eight (8) weeks before the GEC submission deadline for graduate programs, or the SCP submission deadline for undergraduate programs, via the SCP Consultations MS Teams channel. *A completed consultation form for each consultation must be submitted with the final proposal. If non-standard tuition and/or special fees are proposed, complete and submit tuition template to AVPAP separate from the proposal. | Approval steps for new micro-certificate programs as per the VPAC website. Internal consultation template on VPAC website. Non-standard tuition template on VPAC site. | Academic unit | All consultations must have supporting documentation |
| 5 | - Resource requirements approval (signed by the Faculty Dean) *Please complete the New and Revised Academic Program Resource Requirement template and submit to the VPAC office a minimum of eight (8) weeks prior to submitting this proposal to the Senate Committee on Planning. | New and Revised Academic Program Resource Requirement template on VPAC website. | Academic unit | The New and Revised Academic Program Resource Requirement template should be submitted separately to the AVPAP only. This is not part of the proposal as resources are not considered by SCP; however, resource requirements are considered by the Board of Governors. |
| 6 | Template (proposal) submitted to Senate Committee on Planning (SCP) for approval. |  | Academic unit and Dean make a short presentation to SCP and respond to questions. | Faculty Dean or designate makes a short presentation to SCP and responds to questions. |